## Project Plan
| Project Title | STATUS
| What The Food? | Not Started |  |  |  |  | Project Duration
| Team Leader | In Progress |  |  | Start Date | End Date | in Days
| Daniel Ramirez | Complete |  |  | 2022-01-31 | 2022-05-15 | 105
On Hold
Task ID | Business Item | Status | Programmer 1 | Supporting Member | Start Date | End Date | Duration in Days | Comments
Sprint 1 Begins (1/31- 2/6)
1 | Extra Feature(s) | Complete |  |  | 2022-01-31 | 2022-02-06 | 7
1.1 | -Add new features to BRD | Complete | Luke | Not Assigned | 2022-01-31 | 2022-02-03 | 4 | Add the new features to the BRD
1.2 | - Add new features to any affected documents | Complete | Luke | Daniel | 2022-02-01 | 2022-02-03 | 3 | Add the new features to any requisite documents
1.3 | -Update project plan | Not Started | Daniel | Luke | 2022-02-02 | 2022-02-05 | 4 | Update project plan to account for new member and features
2 | Data Access Layer | Complete |  |  | 2022-01-31 | 2022-02-06 | 7
2.1 | -Creation of a DAL class. Create proper context connections. | Complete | Matthew | Tyler | 2022-01-31 | 2022-02-01 | 2 | Class file for the DAL, it will wrap the ORM. Add functioning context connections to the database. NOTE: this may require the DAL class to be able to create objects for each DB table from input information.
2.2 | -Population of DAL class with functions that will access and alter the DB | Complete | Matthew | Tyler | 2022-02-02 | 2022-02-05 | 4 | Additions of functions such as ADD to table, DELETE from table, UPDATE table, etc.
2.3 | - Update outdated codebase to account for DAL. | Complete | Matthew | Tyler | 2022-02-05 | 2022-02-06 | 2 | This means going through old code and updating it to conform the the new DB access method.
Sprint 1 End (2/6)
Sprint 2 Start (2/7 - 2/13) 7 days
3 | Fix Account Class | Not Started |  |  | 2022-02-07 | 2022-02-13 | 7
3.1 | -Fix account class to better fit out class diagram. | Not Started | Tyler | Matthew | 2022-02-07 | 2022-02-09 | 3 | Now with a proper DAL we can fix our Account class to better fit our planned class diagram. Either a decorator pattern or similar structure.
3.2 | -Unit Testing | Not Started | Tyler | Matthew | 2022-02-10 | 2022-02-11 | 2 | Test added code
4 | Micro-Service Connector | Not Started |  |  | 2022-02-07 | 2022-02-13 | 7
4.1 | -Creation of microservice classes | Not Started | Daniel | Luke | 2022-02-07 | 2022-02-09 | 3 | Class file for each microservice specified on the network diagram
4.2 | - Creation of methods to connect the according services through the specified ports | Not Started | Daniel | Luke | 2022-02-09 | 2022-02-13 | 5 | Threads/tasks for communication between the desired processes, needs to be able to send a json file
5 | AMR Microservice Functionality | Not Started |  |  | 2022-02-07 | 2022-02-13 | 7
5.1 | -Connect AMR to the database | Not Started | Hunter | Alex | 2022-02-07 | 2022-02-15 | 9 | Add a table to the database to hold AMR informatinon.
5.1 | -Add appropriate functions to the AMR class. | Not Started | Michelle | Alex | 2022-02-16 | 2022-02-12 | -3 | Add methods for the AMR function. Methods that will provide the service worker with information on a user's amr IF it exists, as well as functinons that will update/set a user's AMR information if given.
5.2 | -Unit Testing | Not Started | Hunter | Matthew | 2022-02-12 | 2022-02-13 | 2 | Test added code
Sprint 2 End (2/13)
Sprint 3 Start (2/14 - 2/20) 14 days
6 | Login/Landing Page | Not Started |  |  | 2022-02-14 | 2022-02-20 | 7
6.1 | -Create the landing/login page. | Not Started | Tyler | Michelle | 2022-02-14 | 2022-02-17 | 4 | create a barebones login page that takes in login info to allow user access. ALSO allow users to create an account. Simply take in input.
6.2 | -create functionality to let people log in | Not Started | Tyler | Michelle | 2022-02-17 | 2022-02-19 |  | Connect the login page to the database to allow for user addition and validation.
6.3 | -Testing | Not Started | Hunter | Tyler | 2022-02-19 | 2022-02-20
7 | Micro-Service Connector | Not Started |  |  | 2022-02-07 | 2022-02-13 | 7
7.1 | -Encoder and decoder functions for JSON files | Not Started | Alex | Daniel | 2022-02-07 | 2022-02-10 | 4 | Make a common functions that will be used to wrap/unwrap functions in JSON files
7.2 | -Unit Testing | Not Started | Daniel | Matthew | 2022-02-11 | 2022-02-13 | 3 | Test added code
Sprint 3 End (2/20)
Sprint 4 Begins (2/21 - 2/27)
8 | Site Navigation | Not Started |  |  | 2022-02-28 | 2022-03-06 | 7
8.1 | - Create bare homepage. | Not Started | Tyler | Matthew | 2022-02-28 | 2022-03-02 | 3 | create a page that will act as the homepage. News will be put here.
8.2 | - Create naviagtion bar | Not Started | Tyler | Daniel | 2022-03-03 | 2022-03-04 | 2 | create a navigation bar that will send the user to the scan, food alternatives, AMR, history, settings, and home page.
8.3 | - Create bare versions of scan, food alternatives, AMR, history, and settings. | Not Started | Daniel | Tyler | 2022-03-04 | 2022-03-06 | 3 | create bare versions of these pages for the website to confirma working navigation.
9 | Food flags Creation | Not Started |  |  | 2022-02-21 | 2022-02-27 | 7
9.1 | -create food flags class and add to database | Not Started | Michelle | Daniel | 2022-02-21 | 2022-02-23 | 3 | creation of the food flags class and add it to the database.
9.2 | -add functinons that will add and remove food flags from users | Not Started | Luke | Alex | 2022-02-23 | 2022-02-25 | 3 | add appropriate functions that will allow us to flag and unflag users for certain ingredients
9.3 | -Unit Testing | Not Started | Alex | Matthew | 2022-02-26 | 2022-02-27 | 2 | Test added code
Sprint 4 End (2/27)
Sprint 5 Begins (2/28 - 3/6)
10 | Reviews Creation | Not Started |  |  | 2022-02-28 | 2022-03-06 | 7
10.1 | -create reviews class and add to database | Not Started | Hunter | Alex | 2022-02-28 | 2022-03-02 | 3 | creation of the reviews class and add it to the database
10.2 | -add functions that allow users to make reviews | Not Started | Luke | Michelle | 2022-03-02 | 2022-03-04 | 3 | add appropriate functinos that allow users to post reviews on a food item
10.3 | -Unit Testing | Not Started | Tyler | Alex | 2022-03-05 | 2022-03-06 | 2 | Test added code
11 | News aggregation | Not Started |  |  | 2022-02-28 | 2022-03-06 | 7 | 14 days
11.1 | - Python web scrape new headlines together related to health | Not Started | Matthew | Daniel | 2022-02-28 | 2022-03-06 | 7 | News should be relevant to not only the product but to the consumer as well. Nothing from a personal blog or something heavily opinionated.
Sprint 5 Ends (3/6)
Sprint 6 Begins (3/7 - 3/13)
11 | News aggregation | Not Started |  |  | 2022-03-07 | 2022-03-13 | 7 | 14 days
11.2 | - create news template on the homepage that will display found news | Not Started | Tyler | Alex | 2022-03-07 | 2022-03-09 | 3 | add the news template to our frontend that will later be connected with our backend algorithm
11.3 | - connect the news aggregation code to the frontend to display found news | Not Started | Daniel | Tyler | 2022-03-09 | 2022-03-11 | 3 | Connect the front end and back end code in order to show users various news articles.
11.4 | -Unit Testing | Not Started | Matthew | Hunter | 2022-03-12 | 2022-03-13 | 2 | Test added code
13 | Food Information Page | Not Started |  |  | 2022-03-07 | 2022-03-13 | 7 | 14 days
13.1 | -Create algorithm that will take a foods ingredients and translate them into simple terms | Not Started | Luke | Alex | 2022-03-07 | 2022-03-10 | 4 | Create an algorithm that will take a given foods ingredients and "translate" them into simple digestable terms.
13.2 | - Display product name, Calories, ingredients, product image | Not Started | Michelle | Hunter | 2022-03-11 | 2022-03-13 | 3 | Create a display on the front end that will neatly present information of a given food item.
Sprint 6 Ends (3/13)
Sprint 7 Begins (3/14 - 3/20)
14 | Review Page | Not Started |  |  | 2022-03-14 | 2022-03-20 | 7 | 8 days
14.1 | - Allow for users to leave reviews on the product they are looking at | Not Started | Hunter | Matthew | 2022-03-14 | 2022-03-16 | 3 | Make sure user can quickly write a review about the product without restricting their opinions. Consider compatibility with profanity filter below as well.
14.2 | - Allow users to read reviews from other customers | Not Started | Matthew | Hunter | 2022-03-16 | 2022-03-18 | 3 | Users should be able to access other user opinions with ease so that they have a general idea regarding the feedback on a product.
14.3 | - Aggregate average review score from internet to set a baseline | Not Started | Daniel | Luke | 2022-03-18 | 2022-03-19 | 2 | Make sure to sum all review left on a product and correctly display the average score that had been made. Make sure that the average is calculated correctly as well.
14.4 | -Unit Testing | Not Started | Luke | Daniel | 2022-03-19 | 2022-03-20 | 2 | Test added code
13 | Food Information Page | Not Started |  |  | 2022-03-14 | 2022-03-20 | 7 | 8 days
13.3 | - Create graphical representation of current and previously scanned foods nutrition | Not Started | Alex | Tyler | 2022-03-14 | 2022-03-17 | 4 | On the front end take the current food item and the users 4 previous scans (if available) and compare them graphically for the user. IF the user has AMR informatinon on file change the graphical range to be that of their personal AMR
13.4 | - Allow the user to click on individual ingredients and have a breakdown of what that ingredient is be shown | Not Started | Tyler | Alex | 2022-03-17 | 2022-03-19 | 3 | On the front end have the user be able to click on the displayed ingredients of the food and display a more in depth description of that ingredient be shown.
13.5 | -Unit Testing | Not Started | Daniel | Michelle | 2022-03-19 | 2022-03-20 | 2 | Test added code
Sprint 7 Ends (3/20)
Sprint 8 Begins (3/21 - 3/27)
15 | AMR Page | Not Started |  |  | 2022-03-21 | 2022-03-27 | 7
15.1 | - page taking in needed information to calculate AMR | Not Started | Michelle | Daniel | 2022-03-21 | 2022-03-24 | 4 | Be able to accurately obtain any user input and calculate the proper results
15.3 | - Integrate with food information to modify daily % values based on personal AMR | Not Started | Daniel | Michelle | 2022-03-24 | 2022-03-26 | 3 | Create compatibility with Food Information and make sure that any modifications made are adjusted accordingly
15.4 | -Unit testing | Not Started | Tyler | Hunter | 2022-03-26 | 2022-03-27 | 2 | Test added code
16 | Food Alternative | Not Started |  |  | 2022-03-21 | 2022-03-27 | 7
16.1 | -Create algorithm that will find similar foods |  | Matthew | Alex | 2022-03-21 | 2022-03-24 | 4 | upon scanning a new food, compare it to current foods in the databases and add similar foods to it to a list, and add itself to the other foods list
16.2 | -Create food alternative page to show users |  | Alex | Tyler | 2022-03-25 | 2022-03-27 | 3 | on the front end add a the display to search for certain foods and alternatives to them
Sprint 8 Ends (3/27)
Sprint 9 Begins (3/28 - 4/3) //spring break
| Account Recovery (OPTIONAL) |  |  |  | 2022-03-28 | 2022-04-03 | 7
| -Add account recovery to login page |  | Not Assigned | Not Assigned | 2022-03-28 | 2022-04-03 | 7 | create a way for a user to recover their account if they have forgotten their password
| Code Cleanup (OPTIONAL) |  |  |  | 2022-03-28 | 2022-04-03 | 7
| -Go through and refactor any code |  | Not Assigned | Not Assigned | 2022-03-28 | 2022-04-03 | 7 | fix any spaghetti code and/or optimize
Sprint 9 Ends (4/3)
Sprint 10 Begins (4/4 - 4/10)
16 | Food Alternative | Not Started |  |  | 2022-04-04 | 2022-04-10 | 7
16.1 | -add quick search for food alternatives to existing food information page |  | Alex | Tyler | 2022-04-04 | 2022-04-07 | 4 | on the food information page add a say to quick search food alternatives for the current displayed food
16.2 | -unit testing |  | Matthew | Daniel | 2022-04-08 | 2022-04-10 | 3 | Test added code
17 | Food Scan |  |  |  | 2022-04-04 | 2022-04-10 | 7
17.1 | -Add functionality that allows the user to take/upload an image of a barcode and nutrition label |  | Daniel | Matthew | 2022-04-04 | 2022-04-10 | 7 | through either image recognition developed in house or one approved (if found) decipher an image of a barcode or food label
Sprint 10 Ends (4/10)
Sprint 11 Begins (4/11 - 4/17)
17 | Food Scan |  |  |  | 2022-04-11 | 2022-04-17 | 7
17.2 | -Continue adding the food scan feature. |  | Daniel | Luke | 2022-04-11 | 2022-04-17 | 7 | same as above
18 | History |  |  |  | 2022-04-11 | 2022-04-17 | 7
18.1 | -Create the history page |  | Alex | Tyler | 2022-04-11 | 2022-04-15 | 5 | create the frontend that will show current logged in users their most recent scans (see BRD for specifics)
18.2 | -unit testing |  | Alex | Tyler | 2022-04-16 | 2022-04-17 | 2 | Test added code
Sprint 11 Ends (4/17)
Sprint 12 Begins (4/18 - 4/24)
17 | Food Scan |  |  |  | 2022-04-18 | 2022-04-24 | 7
17.3 | -Add the front end for the food scan page |  | Tyler | Matthew | 2022-04-18 | 2022-04-21 | 4 | create the page that the user will interact with to search/scan foods.
17.4 | -allow users to upload new food items |  | Tyler | Luke | 2022-04-21 | 2022-04-23 | 3 | create interfance that users can upload food items to, if the current item isn't in the database currently
17.5 | -unit testing |  | Michelle | Hunter | 2022-04-23 | 2022-04-24 | 2 | Test added code
19 | Settings |  |  |  | 2022-04-18 | 2022-04-24 | 7
19.1 | -Create the settings page that will allow logged in users to control certain aspects of their account |  | Alex | Daniel | 2022-04-18 | 2022-04-22 | 5 | create the page that users will interact with to change certain settings for their account. See documents for specifics. This page will link to the food flags.
19.2 | -unit testing |  | Daniel | Michelle | 2022-04-23 | 2022-04-24 | 2 | Test added code
Sprint 12 Ends (4/24)
Sprint 13 Begins (4/25 - 5/1)
20 | Food Flags |  |  |  | 2022-04-25 | 2022-05-01 | 7
20.1 | -Create the food flag interface |  | Luke | Daniel | 2022-04-25 | 2022-04-28 | 4 | create the page that users will interact with to flag certain foods and ingredients to be notified of when viewing a certain food item's information page.
20.2 | -Add the food flag notification functionality to the food information page |  | Tyler | Luke | 2022-04-28 | 2022-04-30 | 3 | add the food flag notification functionality to the food information page depending on a logged in users information
20.3 | -unit testing |  | Hunter | Alex | 2022-04-30 | 2022-05-01 | 2 | Test added code
21 | Public Account Viewing |  |  |  | 2022-04-25 | 2022-05-01 | 7
21.1 | -Add public account page |  | Daniel | Michelle | 2022-04-25 | 2022-04-29 | 5 | From a user review, allow the viewing of that poster's account to view basic information. E.g. how many reviews , scans, and posts they have.
21.2 | -unit testing |  | Matthew | Luke | 2022-04-30 | 2022-05-01 |  | Test added code
Sprint 13 Ends (5/1)
Sprint 14 Begins (5/2 - 5/8)
22 | System wide testing | Not Started |  |  | 2022-05-02 | 2022-05-08 | 7
22.1 | Retest all components with intent to find obscure ways to break the application | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | All portions were tested during development via automated processes. Here you will attempt to abuse edge cases to crash our application or get it to exhibit unintended behavior
22.2 | Fix any edge cases found during this last testing phase | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | Any unintended behaviors found through manual exploitation will be patched here before moving into production
22.3 | Attempt to hack application and patch any exploits | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | Use inside knowledge of how the system interacts to attempt to hijack user information such as passwords or any personal information
22.4 | Fix any security vulnerabilities discovered at this time | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | If any possible methods are found, patch them and reattempt to break in. This repeats until the application is able to safely secure user information
Sprint 14 Ends (5/8)
Sprint 15 Begins (5/9 - 5/15)
23 | Deploy |  |  |  | 2022-05-09 | 2022-05-15 | 7
23.1 | Release product to the public |  | Not Assigned | Not Assigned | 2022-05-09 | 2022-05-15 | 7 | Great job everyone!
Sprint 15 Ends (5/15)

## Risk
Risk ID | Risk Type | Risk Description | Impact(1-5) | Likelyhood(%) | Risk Approach | Strategy
1 | Project Development | Due to our group members taking other courses, some objectives within out SPRINT may not be completed as scheduled | 5 | 100% | Avoidance | Our team will be utilizing Pair Programming. Due to the unpredictable nature of class schedules and work load variations having both members of a two person team free at the same times will be difficult.To maximize productive hours, 3 programmers will be assigned to tasks. While only two will ever work on the task together at any one time, having three increases the number of possible working hours.
2 | Project Execution | Project may not function as intended due to numerous people working on different portions of the project | 5 | 60% | Avoidance | We will set a firm coding standard which will be strictly followed. Furthermore, we will have frequent standup meetings to keep everyone on track with what assignment each individual is currently tasked with.
3 | Access to Resource | Existing API (barcode) stops being supported or otherwise becomes unusable | 3 | 25% | Mitigation | Find a supplementary API that has similar features to the one we were using before. Otherwise we will create our own barcode scanner which incorporates every feature we seek.
4 | Access to Resource | Chrome browser Update causes compatibility issues | 5 | 25% | Acceptance | Require users to use a supported version of chrome to use our web application
5 | Project Execution | Lack of productivity amongst group members | 4 | 5% | Mitigation | Use of scrum to uphold individual accountability and ensure steady workflow through the use of meetings and kanban boards.
6 | Project Development | Project Manager lacks organization | 3 | 10% | Mitigation | Replace Manager or scrum master with a different member
7 | Project Execution | Inaccurate Estimation of Workload | 4 | 80% | Mitigation | We will learn though each iteration how long it takes for us to complete a task and adjust accordingly by our next task.