## Project Plan
| Project Title | STATUS
| What The Food? | Not Started |  |  |  |  | Project Duration
| Team Leader | In Progress |  |  | Start Date | End Date | in Days
| Daniel Ramirez | Complete |  |  | 2022-01-31 | 2022-05-15 | 105
On Hold
Task ID | Business Item | Status | Programmer 1 | Supporting Member | Start Date | End Date | Duration in Days | Comments
Sprint 1 Begins (1/31- 2/6)
1 | Extra Feature(s) | Complete |  |  | 2022-01-31 | 2022-02-06 | 7
1.1 | -Add new features to BRD | Complete | Luke | Not Assigned | 2022-01-31 | 2022-02-03 | 4 | Add the new features to the BRD
1.2 | - Add new features to any affected documents | Complete | Luke | Daniel | 2022-02-01 | 2022-02-03 | 3 | Add the new features to any requisite documents
1.3 | -Update project plan | Complete | Daniel | Luke | 2022-02-02 | 2022-02-05 | 4 | Update project plan to account for new member and features
2 | Data Access Layer | Complete |  |  | 2022-01-31 | 2022-02-06 | 7
2.1 | -Creation of a DAL class. Create proper context connections. | Complete | Matthew | Tyler | 2022-01-31 | 2022-02-01 | 2 | Class file for the DAL, it will wrap the ORM. Add functioning context connections to the database. NOTE: this may require the DAL class to be able to create objects for each DB table from input information.
2.2 | -Population of DAL class with functions that will access and alter the DB | Complete | Matthew | Tyler | 2022-02-02 | 2022-02-05 | 4 | Additions of functions such as ADD to table, DELETE from table, UPDATE table, etc.
2.3 | - Update outdated codebase to account for DAL. | Complete | Matthew | Tyler | 2022-02-05 | 2022-02-06 | 2 | This means going through old code and updating it to conform the the new DB access method.
Sprint 1 End (2/6)
Sprint 2 Start (2/7 - 2/13) 7 days
3 | Fix Account Class | Complete |  |  | 2022-02-07 | 2022-02-13 | 7
3.1 | -Fix account class to better fit out class diagram. | Complete | Tyler | Matthew | 2022-02-07 | 2022-02-09 | 3 | Now with a proper DAL we can fix our Account class to better fit our planned class diagram. Either a decorator pattern or similar structure.
3.2 | -Unit Testing | Complete | Tyler | Matthew | 2022-02-10 | 2022-02-11 | 2 | Test added code
4 | Micro-Service Connector | Complete |  |  | 2022-02-07 | 2022-02-13 | 7
4.1 | -Creation of microservice classes | Complete | Daniel | Luke | 2022-02-07 | 2022-02-09 | 3 | Class file for each microservice specified on the network diagram
4.2 | - Creation of methods to connect the according services through the specified ports | Complete | Daniel | Luke | 2022-02-09 | 2022-02-13 | 5 | Threads/tasks for communication between the desired processes, needs to be able to send a json file
5 | AMR Microservice Functionality | Complete |  |  | 2022-02-07 | 2022-02-13 | 7
5.1 | -Connect AMR to the database | Complete | Hunter | Alex | 2022-02-07 | 2022-02-08 | 2 | Add a table to the database to hold AMR informatinon.
5.1 | -Add appropriate functions to the AMR class. | Complete | Michelle | Alex | 2022-02-09 | 2022-02-12 | 4 | Add methods for the AMR function. Methods that will provide the service worker with information on a user's amr IF it exists, as well as functions that will update/set a user's AMR information if given.
5.2 | -Unit Testing | Complete | Hunter | Matthew | 2022-02-12 | 2022-02-13 | 2 | Test added code
Sprint 2 End (2/13)
Sprint 3 Start (2/14 - 2/20) 14 days
6 | Login/Landing Page | Complete |  |  | 2022-02-14 | 2022-02-20 | 7
6.1 | -Create the landing/login page. | Complete | Tyler | Michelle | 2022-02-14 | 2022-02-17 | 4 | create a barebones login page that takes in login info to allow user access. ALSO allow users to create an account. Simply take in input.
6.2 | -create functionality to let people log in | Complete | Tyler | Michelle | 2022-02-17 | 2022-02-19 |  | Connect the login page to the database to allow for user addition and validation.
6.3 | -Testing | Complete | Hunter | Tyler | 2022-02-19 | 2022-02-20
7 | Micro-Service Connector | Complete |  |  | 2022-02-07 | 2022-02-13 | 7
7.1 | -Encoder and decoder functions for JSON files | Complete | Alex | Daniel | 2022-02-07 | 2022-02-10 | 4 | Make a common functions that will be used to wrap/unwrap functions in JSON files
7.2 | -Unit Testing | Complete | Daniel | Matthew | 2022-02-11 | 2022-02-13 | 3 | Test added code
Sprint 3 End (2/20)
Sprint 4 Begins (2/21 - 2/27)
8 | Site Navigation | Complete |  |  | 2022-02-28 | 2022-03-06 | 7
8.1 | - Create bare homepage. | Complete | Tyler | Michelle | 2022-02-28 | 2022-03-02 | 3 | create a page that will act as the homepage. News will be put here.
8.2 | - Create naviagtion bar | Complete | Tyler | Michelle | 2022-03-03 | 2022-03-04 | 2 | create a navigation bar that will send the user to the scan, food alternatives, AMR, history, settings, and home page.
8.3 | - Create bare versions of scan, food alternatives, AMR, history, and settings. | Complete | Hunter | Tyler | 2022-03-04 | 2022-03-06 | 3 | create bare versions of these pages for the website to confirma working navigation.
9 | Food flags Creation | Complete |  |  | 2022-02-21 | 2022-02-27 | 7
9.1 | -create food flags class and add to database | Complete | Matthew | Alex | 2022-02-21 | 2022-02-23 | 3 | creation of the food flags class and add it to the database.
9.2 | -add functinons that will add and remove food flags from users | Complete | Matthew | Alex | 2022-02-23 | 2022-02-25 | 3 | add appropriate functions that will allow us to flag and unflag users for certain ingredients
9.3 | -Unit Testing | Complete | Alex | Matthew | 2022-02-26 | 2022-02-27 | 2 | Test added code
Sprint 4 End (2/27)
Sprint 5 Begins (2/28 - 3/6)
10 | Reviews Creation | Complete |  |  | 2022-02-28 | 2022-03-06 | 7
10.1 | -create reviews class and add to database | Complete | Tyler | Alex | 2022-02-28 | 2022-03-02 | 3 | creation of the reviews class and add it to the database
10.2 | -add functions that allow users to make reviews | On Hold | Alex | Michelle | 2022-03-02 | 2022-03-04 | 3 | add appropriate functinos that allow users to post reviews on a food item
10.3 | -Unit Testing | On Hold | Tyler | Alex | 2022-03-05 | 2022-03-06 | 2 | Test added code
10 | UM + Unit Tests | Complete |  |  | 2022-02-28 | 2022-03-06 | 7
10.1 | -Finish up user management functions that supports our backend architecture | Complete | Matthew | Alex | 2022-02-28 | 2022-03-02 | 3 | Finish adding the last of UM needed for project functionality and fix current issues with it.
10.2 | -Testing | Complete | Alex | Matthew | 2022-03-02 | 2022-03-04 | 3 | Test added code
10 | Login Page | Complete |  |  | 2022-02-28 | 2022-03-06 | 7
10.1 | -Create frontend landing page that allows for user login | Complete | Hunter | Tyler | 2022-02-28 | 2022-03-02 | 3 | Create a landing page for the site that allows users to login, doing so successfully will lead them to the site homepage.
10.2 | -Testing | Complete | Tyler | Hunter | 2022-03-02 | 2022-03-04 | 3 | Test added code
Sprint 5 Ends (3/6)
Sprint 6 Begins (3/7 - 3/13)
| Connect Front End |  |  |  | 2022-03-07 | 2022-03-10 | 4
| -Connect the frontend for login to the backend functionality for login validation | Complete | Tyler | Luke | 2022-03-07 | 2022-03-09 | 3 | Create the connection between our frontend and backend that allows for full login functionality.
| -Testing | Complete | Tyler | Daniel | 2022-03-09 | 2022-03-10 | 2 | Test Added code
10 | Signup Functionality | Complete |  |  | 2022-03-10 | 2022-03-13 | 4
10.1 | Add funcionality to allow for users to signup | Complete | Hunter | Tyler | 2022-03-10 | 2022-03-12 | 3 | Add to our login page the ability for users to signup for the website and connect this functionality to the backend
10.2 | -Testing | Complete | Tyler | Hunter | 2022-03-12 | 2022-03-13 | 2 | Test added code
10 | Reviews Creation | Complete |  |  | 2022-03-07 | 2022-03-11 | 5
10.1 | -create reviews class and add to database | Complete | Matthew | Alex | 2022-03-07 | 2022-03-08 | 2 | creation of the reviews class and add it to the database
10.2 | -add functions that allow users to make reviews | On Hold | Michelle | Michelle | 2022-03-08 | 2022-03-10 | 3 | add appropriate functinos that allow users to post reviews on a food item
10.3 | -Unit Testing | On Hold | Daniel | Alex | 2022-03-10 | 2022-03-12 | 3 | Test added code
Sprint 6 Ends (3/13)
Sprint 7 Begins (3/14 - 3/20)
10 | Update Documents | Complete |  |  | 2022-03-14 | 2022-03-20 | 7
| -Update Network Diagram | Complete | Daniel | Not Assigned | 2022-03-14 | 2022-03-15 | 2 | -Update the network diagram to reflect our projects new structure
10.1 | -Update BRD | Complete | Michelle | Not Assigned | 2022-03-14 | 2022-03-16 | 3 | -Update the BRD to reflect our projects new structure
10.2 | -Update LLD | Complete | Alex | Daniel | 2022-03-14 | 2022-03-20 | 7 | -Update the low level diagram to reflect our projects new structure
10.3 | -Update DB Schema | Complete | Matthew | Daniel | 2022-03-14 | 2022-03-17 | 4 | -Update the database schema to reflect our projects new structure
10 | Update Codebase | Complete |  |  | 2022-03-14 | 2022-03-20 | 7
| -Separate the code into the new microservice strucure | Complete | Luke | Tyler | 2022-03-14 | 2022-03-19 | 6 | -Separate the previous codebase into new projects to account for our reduced microservice structure
10.1 | -Setup all required classes for our database objects | Complete | Matthew | Hunter | 2022-03-14 | 2022-03-17 | 4 | -In the requisite projects, add the proper context classes and object classes to reflect our new database schema
10.2 | -Reconnect our backend to the frontend | Complete | Tyler | Hunter | 2022-03-18 | 2022-03-20 | 3 | -Given the new strucutre of the backend, reconnect it to the frontend to provide funcionality
10.3 | -Unit Testing | Complete | Matthew | Alex | 2022-03-18 | 2022-03-20 | 3 | -Test all the added code
10 | Food Flags Addition | Complete |  |  | 2022-03-14 | 2022-03-20 | 7
| -Create food flags class to add to our DB | Complete | Matthew | Alex | 2022-03-14 | 2022-03-15 |  | -Create the food flags class to add to our database
10.1 | -Create functions that allow for proper functionality for food flags feature | Complete | Matthew | Not Assigned | 2022-03-16 | 2022-03-19 | 4 | -Create classes that will allow users to add and remove food flags, and check for specific flags
10.2 | -Reconnect our backend to the frontend | Complete | Matthew | Not Assigned | 2022-03-19 | 2022-03-20 | 2 | -Unit tests
Sprint 7 Ends (3/20)
Sprint 8 Begins (3/21 - 3/27)
10 | Front End Structure | Complete |  |  | 2022-03-21 | 2022-03-27 | 7
| -Fix issues with front end | Complete | Tyler | Luke | 2022-03-21 | 2022-03-27 | 7 | -Fix the current issues with the frontend displays currently implimented
10.1 | -testing | Complete | Tyler | Hunter | 2022-03-21 | 2022-03-27 | 7 | -Test the view
10 | Add AMR Page | Complete |  |  | 2022-03-21 | 2022-03-27 | 7
| -Add a display page for AMR | Complete | Michelle | Not Assigned | 2022-03-21 | 2022-03-23 | 3 | -Add a view for the AMR feature
| -Add functionality to the display page | In Progress | Michelle | Tyler | 2022-03-23 | 2022-03-26 | 4 | -Add functionality to the AMR page by connecting it with the backend
10.1 | -testing | Not Started | Michelle | Michelle | 2022-03-26 | 2022-03-27 | 2 | -Test the view
10 | Update DB Keys | Complete |  |  | 2022-03-21 | 2022-03-27 | 7
| -Update databse | Complete | Matthew | Not Assigned | 2022-03-21 | 2022-03-23 | 3 | -Update the DB to reflect new keys
Sprint 8 Ends (3/27)
Sprint 9 Begins (3/28 - 4/3) //spring break
11 | News aggregation | Complete |  |  | 2022-03-28 | 2022-04-03 | 7
11.1 | - Web scrape new headlines together related to health | In Progress | Luke | Not Assigned | 2022-03-28 | 2022-03-31 | 4 | News should be relevant to not only the product but to the consumer as well. Nothing from a personal blog or something heavily opinionated.
11.2 | - create news template on the homepage that will display found news | Complete | Luke | Not Assigned | 2022-03-31 | 2022-04-02 | 3 | add the news template to our frontend that will later be connected with our backend algorithm
11.3 | - connect the news aggregation code to the frontend to display found news | Complete | Luke | Not Assigned | 2022-04-02 | 2022-04-03 | 2 | Connect the front end and back end code in order to show users various news articles.
11.4 | Logging Refactor | In Progress |  |  | 2022-03-28 | 2022-04-03 | 7
13 | -Update logging | In Progress | Alex | Not Assigned | 2022-03-28 | 2022-04-01 | 5 | Update current logging feature to account for necessary changes.
13.1 | - Testing | Not Started | Alex | Not Assigned | 2022-04-01 | 2022-04-03 | 3 | Test added code
11.4 | Scan | On Hold |  |  | 2022-03-28 | 2022-04-03 | 7
13 | -Add a manual way to add food to DB | Complete | Daniel | Not Assigned | 2022-03-28 | 2022-03-31 | 4 | Add functionality to add food to the database through manual input
| -Food repo DAR | Complete | Daniel | Not Assigned | 2022-03-31 | 2022-04-02 | 3 | DAR three food repo API's to allow for easy food information lookup and addition
13.1 | - Testing | On Hold | Daniel | Not Assigned | 2022-04-02 | 2022-04-03 | 2 | Test added code
Sprint 9 Ends (4/3)
Sprint 10 Begins (4/4 - 4/10)
13 | Food Information Page | In Progress |  |  | 2022-04-04 | 2022-04-10 | 7
13.1 | -Create algorithm that will take a foods ingredients and translate them into simple terms | On Hold | Tyler | Matthew | 2022-04-04 | 2022-04-07 | 4 | Create an algorithm that will take a given foods ingredients and "translate" them into simple digestable terms.
13.2 | - Display product name, Calories, ingredients, product image | In Progress | Michelle | Hunter | 2022-04-08 | 2022-04-10 | 3 | Create a display on the front end that will neatly present information of a given food item.
11.4 | Scan | In Progress |  |  | 2022-04-04 | 2022-04-10 | 7
13 | -Add ability to add product from the frontend | In Progress | Daniel | Not Assigned | 2022-04-04 | 2022-04-08 | 5 | Allow users to search up a barcode through the scan feature
13.1 | - Testing | Not Started | Daniel | Not Assigned | 2022-04-09 | 2022-04-10 | 2 | Test added code
13 | Food Flags Page | In Progress |  |  | 2022-04-04 | 2022-04-10 | 7
13 | -Add a page to allow users to add and remove food flags | Not Started | Matthew | Not Assigned | 2022-04-04 | 2022-04-08 | 5 | Add rough settings page that will link to the food flags feature
13.1 | - Testing | Not Started | Matthew | Not Assigned | 2022-04-09 | 2022-04-10 | 2 | Test added code
Sprint 10 Ends (4/10)
Sprint 11 Begins (4/11 - 4/17)
13 | Food Information Page | Not Started |  |  | 2022-04-11 | 2022-04-17 | 7
13.3 | - Create graphical representation of current and previously scanned foods nutrition | Not Started | Hunter | Not Assigned | 2022-04-11 | 2022-04-16 | 6 | On the front end take the current food item and the users 4 previous scans (if available) and compare them graphically for the user. IF the user has AMR informatinon on file change the graphical range to be that of their personal AMR
13.4 | - Allow the user to click on individual ingredients and have a breakdown of what that ingredient is be shown | Not Started | Matthew | Alex | 2022-04-11 | 2022-04-15 | 5 | On the front end have the user be able to click on the displayed ingredients of the food and display a more in depth description of that ingredient be shown.
13.5 | -Unit Testing | Not Started | Hunter | Not Assigned | 2022-04-16 | 2022-04-17 | 2 | Test added code
14 | Review Page | Not Started |  |  | 2022-04-11 | 2022-04-17 | 7
14.1 | - Allow for users to leave reviews on the product they are looking at | Not Started | Tyler | Not Assigned | 2022-04-11 | 2022-04-14 | 4 | Make sure user can quickly write a review about the product without restricting their opinions. Consider compatibility with profanity filter below as well.
14.2 | - Allow users to read reviews from other customers | Not Started | Tyler | Not Assigned | 2022-04-14 | 2022-04-15 | 2 | Users should be able to access other user opinions with ease so that they have a general idea regarding the feedback on a product.
14.3 | - Aggregate average review score from internet to set a baseline | Not Started | Tyler | Not Assigned | 2022-04-11 | 2022-04-13 | 3 | Make sure to sum all review left on a product and correctly display the average score that had been made. Make sure that the average is calculated correctly as well.
14.4 | -Unit Testing | Not Started | Tyler | Not Assigned | 2022-04-16 | 2022-04-17 | 2 | Test added code
17 | Food Scan |  |  |  | 2022-04-11 | 2022-04-17 | 7
| -Allow for uploaded photo or real time photo to submit a barcode |  | Daniel |  | 2022-04-11 | 2022-04-15 | 5 | Allow users to upload a photo of a barcode, or request camera access to take a photo
17.2 | -Testing |  | Daniel | Not Assigned | 2022-04-11 | 2022-04-16 | 6 | Testing added code
18 | History |  |  |  | 2022-04-11 | 2022-04-17 | 7
18.1 | -Create the history page |  | Not Assigned | Not Assigned | 2022-04-11 | 2022-04-15 | 5 | create the frontend that will show current logged in users their most recent scans (see BRD for specifics)
18.2 | -unit testing |  | Not Assigned | Not Assigned | 2022-04-16 | 2022-04-17 | 2 | Test added code
Sprint 11 Ends (4/17)
Sprint 12 Begins (4/18 - 4/24)
16 | Food Alternative | Not Started |  |  | 2022-04-18 | 2022-04-24 | 7
16.1 | -Create algorithm that will find similar foods |  | Not Assigned | Not Assigned | 2022-04-18 | 2022-04-22 | 5 | upon scanning a new food, compare it to current foods in the databases and add similar foods to it to a list, and add itself to the other foods list
16.2 | -Create food alternative page to show users |  | Not Assigned | Not Assigned | 2022-04-22 | 2022-04-24 | 3 | on the front end add a the display to search for certain foods and alternatives to them
| Site Metrics |  |  |  | 2022-04-18 | 2022-04-24
| -Add a way for admins to view site metrics |  | Not Assigned | Not Assigned | 2022-04-18 | 2022-04-24 |  | Add a way to view site metrics, a way for admins to log in and check certain stats about the site.
19 | Settings |  |  |  | 2022-04-18 | 2022-04-24 | 7
19.1 | -Create the settings page that will allow logged in users to control certain aspects of their account |  | Alex | Daniel | 2022-04-18 | 2022-04-22 | 5 | create the page that users will interact with to change certain settings for their account. See documents for specifics. This page will link to the food flags.
19.2 | -unit testing |  | Daniel | Michelle | 2022-04-22 | 2022-04-24 | 3 | Test added code
Sprint 12 Ends (4/24)
Sprint 13 Begins (4/25 - 5/1)
20 | Roll Over Work |  |  |  | 2022-04-25 | 2022-05-01 | 7
-Room for any work that has rolled over
21 | Public Account Viewing |  |  |  | 2022-04-25 | 2022-05-01 | 7
21.1 | -Add public account page |  | Daniel | Michelle | 2022-04-25 | 2022-04-29 | 5 | From a user review, allow the viewing of that poster's account to view basic information. E.g. how many reviews , scans, and posts they have.
21.2 | -unit testing |  | Matthew | Luke | 2022-04-30 | 2022-05-01 | 2 | Test added code
Sprint 13 Ends (5/1)
Sprint 14 Begins (5/2 - 5/8)
22 | System wide testing | Not Started |  |  | 2022-05-02 | 2022-05-08 | 7
22.1 | Retest all components with intent to find obscure ways to break the application | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | All portions were tested during development via automated processes. Here you will attempt to abuse edge cases to crash our application or get it to exhibit unintended behavior
22.2 | Fix any edge cases found during this last testing phase | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | Any unintended behaviors found through manual exploitation will be patched here before moving into production
22.3 | Attempt to hack application and patch any exploits | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | Use inside knowledge of how the system interacts to attempt to hijack user information such as passwords or any personal information
22.4 | Fix any security vulnerabilities discovered at this time | Not Started | Not Assigned | Not Assigned | 2022-05-02 | 2022-05-08 | 7 | If any possible methods are found, patch them and reattempt to break in. This repeats until the application is able to safely secure user information
Sprint 14 Ends (5/8)
Sprint 15 Begins (5/9 - 5/15)
23 | Deploy |  |  |  | 2022-05-09 | 2022-05-15 | 7
Sprint 15 Ends (5/15)

## Risk
Risk ID | Risk Type | Risk Description | Impact(1-5) | Likelyhood(%) | Risk Approach | Strategy
1 | Project Development | Due to our group members taking other courses, some objectives within out SPRINT may not be completed as scheduled | 5 | 100% | Avoidance | Our team will be utilizing Pair Programming. Due to the unpredictable nature of class schedules and work load variations having both members of a two person team free at the same times will be difficult.To maximize productive hours, 3 programmers will be assigned to tasks. While only two will ever work on the task together at any one time, having three increases the number of possible working hours.
2 | Project Execution | Project may not function as intended due to numerous people working on different portions of the project | 5 | 60% | Avoidance | We will set a firm coding standard which will be strictly followed. Furthermore, we will have frequent standup meetings to keep everyone on track with what assignment each individual is currently tasked with.
3 | Access to Resource | Existing API (barcode) stops being supported or otherwise becomes unusable | 3 | 25% | Mitigation | Find a supplementary API that has similar features to the one we were using before. Otherwise we will create our own barcode scanner which incorporates every feature we seek.
4 | Access to Resource | Chrome browser Update causes compatibility issues | 5 | 25% | Acceptance | Require users to use a supported version of chrome to use our web application
5 | Project Execution | Lack of productivity amongst group members | 4 | 5% | Mitigation | Use of scrum to uphold individual accountability and ensure steady workflow through the use of meetings and kanban boards.
6 | Project Development | Project Manager lacks organization | 3 | 10% | Mitigation | Replace Manager or scrum master with a different member
7 | Project Execution | Inaccurate Estimation of Workload | 4 | 80% | Mitigation | We will learn though each iteration how long it takes for us to complete a task and adjust accordingly by our next task.