## Percent Error
| Total Sprint Number | Predicted Work | Work Done | Percent Error
Fist Semester Sprint 0 | Sem 1 Sprint 0 | 79.5 | 74 | 6.9182
Fist Semester Sprint 1 | Sem 1 Sprint 1 | 47.5 | 58 | -22.1053
Fist Semester Sprint 2 | Sem 1 Sprint 2 | 47.5 | 52 | -9.4737
Fist Semester Sprint 3 | Sem 1 Sprint 3 | 58.5 | 60 | -2.5641
Fist Semester Sprint 4 | Sem 1 Sprint 4 | 64.5 | 72 | -11.6279
Fist Semester Sprint 5 | Sem 1 Sprint 5 | 58 | 58 | 0
Fist Semester Sprint 6 | Sem 1 Sprint 6 | 86.5 | 80 | 7.5145
Second Semester Sprint 1 | Sem 2 Sprint 1 | 50 | 42 | 16
Second Semester Sprint 2 | Sem 2 Sprint 2 | 45 | 46.5 | -3.3333
Second Semester Sprint 3 | Sem 2 Sprint 3 | 50 | 49 | 2
Second Semester Sprint 4 | Sem 2 Sprint 4 | 50 | 58.5 | -17
Second Semester Sprint 5 | Sem 2 Sprint 5 | 60 | 59.5 | 0.83333
Second Semester Sprint 6 | Sem 2 Sprint 6 | 55 | 54.5 | 0.90909
Second Semester Sprint 7 | Sem 2 Sprint 7 | 55 | 57.5 | -4.5455
Second Semester Sprint 8 | Sem 2 Sprint 8 | 54 | 49 | 9.2593
Second Semester Sprint 9 | Sem 2 Sprint 9 | 66 | 53 | 19.697
Second Semester Sprint 10 | Sem 2 Sprint 10 | 60 | 59.5 | 0.83333
Second Semester Sprint 11 | Sem 2 Sprint 11 | 94 | 69.5 | 26.0638
Second Semester Sprint 12 | Sem 2 Sprint 12 | 60 | 92.5 | -54.1667
Second Semester Sprint 13 | Sem 2 Sprint 13 | 43 | 56 | -30.2326
Second Semester Sprint 14 | Sem 2 Sprint 14 | 58 | 66 | -13.7931
Second Semester Sprint 15 | Sem 2 Sprint 15 | 40 | 64 | -60

## Sprint 1
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 5 | 2022-01-31 | 51 | 50 | Extra Features | 13 | 20 | 2022-01-31 | 8 | 9 | 8 | 8 | 10 | 8 | 8 | 59 |  | 0.71429 | 0.92857 | 0.57143 | 0.85714 | 1.2857 | 0.92857 | 0.71429
Daniel | 9 | 8.5 | 2022-02-01 | 44 | 42.8571 | Data Access Layer | 16 | 30 | 2022-02-01 | 6.8571 | 7.7143 | 6.8571 | 6.8571 | 8.5714 | 6.8571 | 6.8571 | 50.5714
Hunter | 8 | 6 | 2022-02-02 | 35 | 35.7143 |  | 0 | 0 | 2022-02-02 | 5.7143 | 6.4286 | 5.7143 | 5.7143 | 7.1429 | 5.7143 | 5.7143 | 42.1429
Luke | 8 | 8 | 2022-02-03 | 25 | 28.5714 | Other | 21 | 0 | 2022-02-03 | 4.5714 | 5.1429 | 4.5714 | 4.5714 | 5.7143 | 4.5714 | 4.5714 | 33.7143
Matt | 10 | 9 | 2022-02-04 | 17.5 | 21.4286 | Total Predicted Work |  | 50 | 2022-02-04 | 3.4286 | 3.8571 | 3.4286 | 3.4286 | 4.2857 | 3.4286 | 3.4286 | 25.2857
Michelle | 8 | 6.5 | 2022-02-05 | 13.5 | 14.2857 | Expected Work | Actual Work |  | 2022-02-05 | 2.2857 | 2.5714 | 2.2857 | 2.2857 | 2.8571 | 2.2857 | 2.2857 | 16.8571
Tyler | 8 | 7 | 2022-02-06 | 9 | 7.1429 | 59 | 50 |  | 2022-02-06 | 1.1429 | 1.2857 | 1.1429 | 1.1429 | 1.4286 | 1.1429 | 1.1429 | 8.4286
2022-01-31 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | 0 | 0 |  | 0 |  | 0 | 8 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  |  |  | 2 |  | 2 | 7 |  | 2022-01-31 | 8 | 7 | 6 | 6 | 10 | 8 | 6 | 51
Hunter |  |  |  | 2 | 0 | 2 | 6 |  | 2022-02-01 | 8 | 7 | 3 | 6 | 7 | 7 | 6 | 44
Luke |  | 2 |  |  | 0 | 2 | 6 |  | 2022-02-02 | 6 | 5 | 3 | 4 | 5 | 6 | 6 | 35
Matt | [5 empty] | 0 | 10 |  | 2022-02-03 | 5 | 3 | 2 | 3 | 3 | 5 | 4 | 25
Michelle |  |  |  |  | 0 | 0 | 8 |  | 2022-02-04 | 4 | 0.5 | 2 | 1 | 3 | 4 | 3 | 17.5
Tyler | 2 |  |  |  |  | 2 | 6 |  | 2022-02-05 | 3 | 0.5 | 2 | 1 | 1 | 3 | 3 | 13.5
2022-02-01 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-06 | 3 | 0.5 | 2 | 0 | 1 | 1.5 | 1 | 9
Alex | 0 | 0 |  | 0 | 0 | 0 | 8 |  | 2022-02-07 | 3 | 0.5 | 2 | 0 | 1 | 1.5 | 1 | 9
Daniel | [5 empty] | 0 | 7
Hunter | 3 |  |  |  | 1 | 3 | 3
Luke |  |  |  |  | 0 | 0 | 6
Matt |  | 3 |  |  |  | 3 | 7
Michelle |  |  |  | 1 |  | 1 | 7
Tyler | [5 empty] | 0 | 6
2022-02-02 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 0 | 0 |  | 2 | 0 | 2 | 6
Daniel | 2 |  |  |  | 0.5 | 2 | 5
Hunter | [5 empty] | 0 | 3
Luke |  | 2 |  |  |  | 2 | 4
Matt |  | 2 |  |  |  | 2 | 5
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | [5 empty] | 0 | 6
2022-02-03 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 0 | 0 |  | 1 | 1 | 1 | 5
Daniel | 1 |  |  | 1 | 0.5 | 2 | 3
Hunter | 1 |  |  |  |  | 1 | 2
Luke |  | 1 |  |  |  | 1 | 3
Matt |  | 2 |  |  |  | 2 | 3
Michelle |  |  |  | 1 |  | 1 | 5
Tyler |  | 2 |  |  |  | 2 | 4
2022-02-04 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 4
Daniel | 1 |  |  | 1.5 |  | 2.5 | 0.5
Hunter | [5 empty] | 0 | 2
Luke |  |  |  | 2 | 0 | 2 | 1
Matt | [5 empty] | 0 | 3
Michelle |  |  |  | 1 |  | 1 | 4
Tyler | 1 |  |  |  |  | 1 | 3
2022-02-05 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 3
Daniel | [5 empty] | 0 | 0.5
Hunter | [5 empty] | 0 | 2
Luke |  |  |  |  | 0 | 0 | 1
Matt |  | 2 |  |  |  | 2 | 1
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 3
2022-02-06 | Extra Features | Data Access Layer |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 3
Daniel | [5 empty] | 0 | 0.5
Hunter | [5 empty] | 0 | 2
Luke |  |  |  | 1 | 0 | 1 | 0
Matt | [5 empty] | 0 | 1
Michelle |  |  |  | 1.5 |  | 1.5 | 1.5
Tyler | 2 |  |  |  |  | 2 | 1
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 3
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-01-31 | 8 | 9.8039 | 51 | 51 | 7.2857
2022-02-01 | 7 | -3.9216 | 44 | 43.7143
2022-02-02 | 9 | 23.5294 | 35 | 36.4286
2022-02-03 | 10 | 37.2549 | 25 | 29.1429
2022-02-04 | 7.5 | 2.9412 | 17.5 | 21.8571
2022-02-05 | 4 | -45.098 | 13.5 | 14.5714
2022-02-06 | 4.5 | -38.2353 | 9 | 7.2857
2022-02-07 | 0 | 100 | 9 | 0

## Sprint 2
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 6 | 2022-02-07 | 47 | 45 | Fix Account Class | 6 | 15 | 2022-02-07 | 8 | 8 | 8 | 8 | 6 | 8 | 8 | 54 |  | 0.71429 | 0.85714 | 0.71429 | 0.71429 | 0.85714 | 0.78571 | 1
Daniel | 8 | 8 | 2022-02-08 | 43 | 38.5714 | Microservice Connector | 6 | 20 | 2022-02-08 | 6.8571 | 6.8571 | 6.8571 | 6.8571 | 5.1429 | 6.8571 | 6.8571 | 46.2857
Hunter | 8 | 7 | 2022-02-09 | 33 | 32.1429 | AMR Functionality | 14.5 | 10 | 2022-02-09 | 5.7143 | 5.7143 | 5.7143 | 5.7143 | 4.2857 | 5.7143 | 5.7143 | 38.5714
Luke | 8 | 7 | 2022-02-10 | 23 | 25.7143 | Other | 20 | 0 | 2022-02-10 | 4.5714 | 4.5714 | 4.5714 | 4.5714 | 3.4286 | 4.5714 | 4.5714 | 30.8571
Matt | 6 | 6 | 2022-02-11 | 17 | 19.2857 | Total Predicted Work |  | 45 | 2022-02-11 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 2.5714 | 3.4286 | 3.4286 | 23.1429
Michelle | 8 | 5.5 | 2022-02-12 | 14.5 | 12.8571 | Expected Work | Actual Work |  | 2022-02-12 | 2.2857 | 2.2857 | 2.2857 | 2.2857 | 1.7143 | 2.2857 | 2.2857 | 15.4286
Tyler | 8 | 7 | 2022-02-13 | 7.5 | 6.4286 | 54 | 46.5 |  | 2022-02-13 | 1.1429 | 1.1429 | 1.1429 | 1.1429 | 0.85714 | 1.1429 | 1.1429 | 7.7143
2022-02-07 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  | 1 |  |  | 1 | 7 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  | 2 |  |  |  | 2 | 6 |  | 2022-02-07 | 7 | 6 | 6 | 6 | 6 | 8 | 8 | 47
Hunter |  |  | 2 |  | 1 | 2 | 6 |  | 2022-02-08 | 6 | 6 | 6 | 5 | 6 | 7 | 7 | 43
Luke |  |  |  | 2 |  | 2 | 6 |  | 2022-02-09 | 5 | 4 | 5 | 5 | 3 | 6 | 5 | 33
Matt | [5 empty] | 0 | 6 |  | 2022-02-10 | 4 | 1 | 3 | 4 | 1 | 6 | 4 | 23
Michelle |  |  |  |  | 1 | 0 | 8 |  | 2022-02-11 | 2 | 0 | 2 | 4 | 1 | 5 | 3 | 17
Tyler | [5 empty] | 0 | 8 |  | 2022-02-12 | 2 | 0 | 2 | 3 | 1 | 3.5 | 3 | 14.5
2022-02-08 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-13 | 2 | 0 | 1 | 1 | 0 | 2.5 | 1 | 7.5
Alex |  |  | 1 |  |  | 1 | 6 |  | 2022-02-14 | 2 | 0 | 1 | 1 | 0 | 2.5 | 1 | 7.5
Daniel | [5 empty] | 0 | 6
Hunter | [5 empty] | 0 | 6
Luke |  |  |  | 1 | 1 | 1 | 5
Matt | [5 empty] | 0 | 6
Michelle |  |  |  | 1 |  | 1 | 7
Tyler | 1 |  |  |  |  | 1 | 7
2022-02-09 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 1 |  |  | 1 | 5
Daniel |  | 2 |  |  | 0.5 | 2 | 4
Hunter |  |  | 1 |  |  | 1 | 5
Luke | [5 empty] | 0 | 5
Matt | 3 |  |  |  |  | 3 | 3
Michelle |  |  |  | 1 |  | 1 | 6
Tyler |  |  |  | 2 |  | 2 | 5
2022-02-10 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 1 |  |  | 1 | 4
Daniel |  | 2 |  | 1 |  | 3 | 1
Hunter |  |  | 2 |  |  | 2 | 3
Luke |  |  |  | 1 |  | 1 | 4
Matt | 2 |  |  |  |  | 2 | 1
Michelle |  |  |  |  | 1 | 0 | 6
Tyler |  |  |  | 1 |  | 1 | 4
2022-02-11 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 1 | 1 |  | 2 | 2
Daniel |  |  |  | 1 | 0.5 | 1 | 0
Hunter |  |  | 1 |  |  | 1 | 2
Luke |  |  |  |  | 2 | 0 | 4
Matt | [5 empty] | 0 | 1
Michelle |  |  |  | 1 |  | 1 | 5
Tyler |  |  |  | 1 |  | 1 | 3
2022-02-12 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 0 |  | 1 | 0 | 2
Daniel | [5 empty] | 0 | 0
Hunter | [5 empty] | 0 | 2
Luke |  |  |  | 1 | 1 | 1 | 3
Matt | [5 empty] | 0 | 1
Michelle |  |  | 1.5 |  |  | 1.5 | 3.5
Tyler | [5 empty] | 0 | 3
2022-02-13 | Fix Account Class | Microservice Connector | AMR Functionality | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 0 |  | 1 | 0 | 2
Daniel | [5 empty] | 0 | 0
Hunter |  |  | 1 |  |  | 1 | 1
Luke |  |  |  | 2 |  | 2 | 1
Matt |  |  |  | 1 |  | 1 | 0
Michelle |  |  | 1 |  |  | 1 | 2.5
Tyler |  |  |  | 2 |  | 2 | 1
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 10
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-02-07 | 7 | 4.2553 | 47 | 47 | 6.7143
2022-02-08 | 4 | -40.4255 | 43 | 40.2857
2022-02-09 | 10 | 48.9362 | 33 | 33.5714
2022-02-10 | 10 | 48.9362 | 23 | 26.8571
2022-02-11 | 6 | -10.6383 | 17 | 20.1429
2022-02-12 | 2.5 | -62.766 | 14.5 | 13.4286
2022-02-13 | 7 | 4.2553 | 7.5 | 6.7143
2022-02-14 | 0 | 100 | 7.5 | 0

## Sprint 3
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 6 | 2022-02-14 | 54 | 50 | Login/Landing Page | 14 | 15 | 2022-02-14 | 8 | 8 | 8 | 10 | 8 | 8 | 8 | 58 |  | 0.71429 | 1.0714 | 0.85714 | 0.71429 | 1.1429 | 0.92857 | 1
Daniel | 8 | 7.5 | 2022-02-15 | 46 | 42.8571 | Microservice Connector | 4 | 20 | 2022-02-15 | 6.8571 | 6.8571 | 6.8571 | 8.5714 | 6.8571 | 6.8571 | 6.8571 | 49.7143
Hunter | 8 | 6 | 2022-02-16 | 30 | 35.7143 | Flags+Food Items Class | 14 | 15 | 2022-02-16 | 5.7143 | 5.7143 | 5.7143 | 7.1429 | 5.7143 | 5.7143 | 5.7143 | 41.4286
Luke | 10 | 6 | 2022-02-17 | 24 | 28.5714 | Other | 17 | 0 | 2022-02-17 | 4.5714 | 4.5714 | 4.5714 | 5.7143 | 4.5714 | 4.5714 | 4.5714 | 33.1429
Matt | 8 | 8 | 2022-02-18 | 19 | 21.4286 | Total Predicted Work |  | 50 | 2022-02-18 | 3.4286 | 3.4286 | 3.4286 | 4.2857 | 3.4286 | 3.4286 | 3.4286 | 24.8571
Michelle | 8 | 7.5 | 2022-02-19 | 13 | 14.2857 | Expected Work | Actual Work |  | 2022-02-19 | 2.2857 | 2.2857 | 2.2857 | 2.8571 | 2.2857 | 2.2857 | 2.2857 | 16.5714
Tyler | 8 | 8 | 2022-02-20 | 9 | 7.1429 | 58 | 49 |  | 2022-02-20 | 1.1429 | 1.1429 | 1.1429 | 1.4286 | 1.1429 | 1.1429 | 1.1429 | 8.2857
2022-02-14 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  | 1 |  | 2 | 1 | 7 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | [5 empty] | 0 | 8 |  | 2022-02-14 | 7 | 8 | 8 | 9 | 8 | 7 | 7 | 54
Hunter | [5 empty] | 0 | 8 |  | 2022-02-15 | 5 | 6 | 7 | 9 | 8 | 6 | 5 | 46
Luke |  |  |  | 1 |  | 1 | 9 |  | 2022-02-16 | 2 | 4.5 | 5 | 7 | 5 | 4.5 | 2 | 30
Matt | [5 empty] | 0 | 8 |  | 2022-02-17 | 2 | 3.5 | 5 | 7 | 3 | 3.5 | 0 | 24
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-02-18 | 2 | 1.5 | 4 | 7 | 2 | 2.5 | 0 | 19
Tyler | 1 |  |  |  |  | 1 | 7 |  | 2022-02-19 | 2 | 0.5 | 3 | 4 | 2 | 1.5 | 0 | 13
2022-02-15 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-20 | 2 | 0.5 | 2 | 4 | 0 | 0.5 | 0 | 9
Alex |  |  | 2 |  | 1 | 2 | 5 |  | 2022-02-21 | 2 | 0.5 | 2 | 4 | 0 | 0.5 | 0 | 9
Daniel |  | 1 |  | 1 |  | 2 | 6
Hunter | 1 |  |  |  |  | 1 | 7
Luke | [5 empty] | 0 | 9
Matt | [5 empty] | 0 | 8
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | 2 |  |  |  |  | 2 | 5
2022-02-16 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 3 |  | 1 | 3 | 2
Daniel |  |  |  | 1.5 |  | 1.5 | 4.5
Hunter | 2 |  |  |  |  | 2 | 5
Luke |  |  |  | 2 |  | 2 | 7
Matt |  |  | 3 |  |  | 3 | 5
Michelle |  |  |  | 1.5 |  | 1.5 | 4.5
Tyler | 3 |  |  |  |  | 3 | 2
2022-02-17 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel |  |  |  | 1 |  | 1 | 3.5
Hunter | [5 empty] | 0 | 5
Luke | [5 empty] | 0 | 7
Matt |  |  | 2 |  |  | 2 | 3
Michelle |  |  |  | 1 |  | 1 | 3.5
Tyler | 2 |  |  |  |  | 2 | 0
2022-02-18 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel |  |  |  | 2 | 1 | 2 | 1.5
Hunter | 1 |  |  |  |  | 1 | 4
Luke |  |  |  |  | 3 | 0 | 7
Matt |  |  | 1 |  |  | 1 | 2
Michelle |  |  |  | 1 |  | 1 | 2.5
Tyler | [5 empty] | 0 | 0
2022-02-19 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel |  |  |  | 1 |  | 1 | 0.5
Hunter | 1 |  |  |  |  | 1 | 3
Luke |  | 3 |  |  |  | 3 | 4
Matt | [5 empty] | 0 | 2
Michelle |  |  |  | 1 |  | 1 | 1.5
Tyler | [5 empty] | 0 | 0
2022-02-20 | Login/Landing Page | Microservice Connector | Flags+Food Items Class | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel | [5 empty] | 0 | 0.5
Hunter | 1 |  |  |  |  | 1 | 2
Luke | [5 empty] | 0 | 4
Matt |  |  | 2 |  |  | 2 | 0
Michelle |  |  |  | 1 |  | 1 | 0.5
Tyler | [5 empty] | 0 | 0
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 8
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-02-14 | 4 | -48.1481 | 54 | 54 | 7.7143
2022-02-15 | 8 | 3.7037 | 46 | 46.2857
2022-02-16 | 16 | 107.4074 | 30 | 38.5714
2022-02-17 | 6 | -22.2222 | 24 | 30.8571
2022-02-18 | 5 | -35.1852 | 19 | 23.1429
2022-02-19 | 6 | -22.2222 | 13 | 15.4286
2022-02-20 | 4 | -48.1481 | 9 | 7.7143
2022-02-21 | 0 | 100 | 9 | 0

## Sprint 4
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 8 | 2022-02-21 | 52 | 50 | Site Navigation | 9 | 15 | 2022-02-21 | 8 | 9 | 8 | 10 | 10 | 8 | 8 | 61 |  | 1.1429 | 1.0714 | 0.85714 | 1.1429 | 1.1429 | 1 | 0.71429
Daniel | 9 | 8.5 | 2022-02-22 | 43 | 42.8571 | Food Flags Creation | 10 | 15 | 2022-02-22 | 6.8571 | 7.7143 | 6.8571 | 8.5714 | 8.5714 | 6.8571 | 6.8571 | 52.2857
Hunter | 8 | 8 | 2022-02-23 | 34 | 35.7143 |  | 0 | 0 | 2022-02-23 | 5.7143 | 6.4286 | 5.7143 | 7.1429 | 7.1429 | 5.7143 | 5.7143 | 43.5714
Luke | 10 | 9 | 2022-02-24 | 28.5 | 28.5714 | Other | 37.5 | 20 | 2022-02-24 | 4.5714 | 5.1429 | 4.5714 | 5.7143 | 5.7143 | 4.5714 | 4.5714 | 34.8571
Matt | 10 | 10 | 2022-02-25 | 22.5 | 21.4286 | Total Predicted Work |  | 50 | 2022-02-25 | 3.4286 | 3.8571 | 3.4286 | 4.2857 | 4.2857 | 3.4286 | 3.4286 | 26.1429
Michelle | 8 | 8 | 2022-02-26 | 13.5 | 14.2857 | Expected Work | Actual Work |  | 2022-02-26 | 2.2857 | 2.5714 | 2.2857 | 2.8571 | 2.8571 | 2.2857 | 2.2857 | 17.4286
Tyler | 8 | 7 | 2022-02-27 | 2.5 | 7.1429 | 61 | 58.5 |  | 2022-02-27 | 1.1429 | 1.2857 | 1.1429 | 1.4286 | 1.4286 | 1.1429 | 1.1429 | 8.7143
2022-02-21 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  |  | 0 | 2 | 0 | 8 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  |  |  | 1 | 0.5 | 1 | 8 |  | 2022-02-21 | 8 | 8 | 6 | 9 | 8 | 7 | 6 | 52
Hunter | 2 |  |  |  |  | 2 | 6 |  | 2022-02-22 | 5 | 5 | 6 | 9 | 8 | 6 | 4 | 43
Luke |  |  |  | 1 |  | 1 | 9 |  | 2022-02-23 | 1 | 5 | 4 | 9 | 6 | 5 | 4 | 34
Matt |  | 2 |  |  |  | 2 | 8 |  | 2022-02-24 | 1 | 1.5 | 4 | 9 | 6 | 3 | 4 | 28.5
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-02-25 | 0 | 0.5 | 4 | 8 | 4 | 2 | 4 | 22.5
Tyler |  |  |  | 2 |  | 2 | 6 |  | 2022-02-26 | 0 | 0.5 | 4 | 5 | 2 | 1 | 1 | 13.5
2022-02-22 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-02-27 | 0 | 0.5 | 0 | 1 | 0 | 0 | 1 | 2.5
Alex |  |  |  | 3 |  | 3 | 5 |  | 2022-02-28 | 0 | 0.5 | 0 | 1 | 0 | 0 | 1 | 2.5
Daniel |  |  |  | 2 | 1 | 3 | 5
Hunter | [5 empty] | 0 | 6
Luke | [5 empty] | 0 | 9
Matt | [5 empty] | 0 | 8
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | 2 |  |  |  |  | 2 | 4
2022-02-23 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 4 |  | 4 | 1
Daniel | [5 empty] | 0 | 5
Hunter | 2 |  |  |  |  | 2 | 4
Luke | [5 empty] | 0 | 9
Matt |  | 2 |  |  |  | 2 | 6
Michelle |  |  |  | 1 |  | 1 | 5
Tyler | [5 empty] | 0 | 4
2022-02-24 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 1
Daniel |  |  |  | 2.5 | 1 | 3.5 | 1.5
Hunter | [5 empty] | 0 | 4
Luke | [5 empty] | 0 | 9
Matt | [5 empty] | 0 | 6
Michelle |  |  |  | 2 |  | 2 | 3
Tyler | [5 empty] | 0 | 4
2022-02-25 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 0
Daniel |  |  |  | 1 |  | 1 | 0.5
Hunter | [5 empty] | 0 | 4
Luke |  |  |  | 1 |  | 1 | 8
Matt |  | 2 |  |  |  | 2 | 4
Michelle |  |  |  | 1 |  | 1 | 2
Tyler | [5 empty] | 0 | 4
2022-02-26 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 0
Daniel | [5 empty] | 0 | 0.5
Hunter | [5 empty] | 0 | 4
Luke |  |  |  | 3 |  | 3 | 5
Matt |  | 2 |  |  |  | 2 | 2
Michelle |  |  |  | 1 |  | 1 | 1
Tyler | 3 |  |  |  |  | 3 | 1
2022-02-27 | Site Navigation | Food Flags Creation |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  |  | 2 | 0 | 0
Daniel | [5 empty] | 0 | 0.5
Hunter |  |  |  | 4 |  | 4 | 0
Luke |  |  |  | 4 |  | 4 | 1
Matt |  | 2 |  |  |  | 2 | 0
Michelle |  |  |  | 1 |  | 1 | 0
Tyler | [5 empty] | 0 | 1
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 6.5
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-02-21 | 9 | 21.1538 | 52 | 52 | 7.4286
2022-02-22 | 9 | 21.1538 | 43 | 44.5714
2022-02-23 | 9 | 21.1538 | 34 | 37.1429
2022-02-24 | 5.5 | -25.9615 | 28.5 | 29.7143
2022-02-25 | 6 | -19.2308 | 22.5 | 22.2857
2022-02-26 | 9 | 21.1538 | 13.5 | 14.8571
2022-02-27 | 11 | 48.0769 | 2.5 | 7.4286
2022-02-28 | 0 | 100 | 2.5 | 0

## Sprint 5
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 11 | 2022-02-28 | 57 | 60 | Reviews Creation | 0 | 10 | 2022-02-28 | 8 | 9 | 8 | 8 | 12 | 8 | 12 | 65 |  | 1.2857 | 1.0714 | 0.85714 | 1 | 1 | 0.85714 | 1.2857
Daniel | 9 | 7.5 | 2022-03-01 | 48 | 51.4286 | UM + Unit tests | 4 | 20 | 2022-03-01 | 6.8571 | 7.7143 | 6.8571 | 6.8571 | 10.2857 | 6.8571 | 10.2857 | 55.7143
Hunter | 8 | 8 | 2022-03-02 | 39.5 | 42.8571 | Login/Signup Page | 19 | 20 | 2022-03-02 | 5.7143 | 6.4286 | 5.7143 | 5.7143 | 8.5714 | 5.7143 | 8.5714 | 46.4286
Luke | 8 | 8 | 2022-03-03 | 30 | 34.2857 | Other | 30.5 | 10 | 2022-03-03 | 4.5714 | 5.1429 | 4.5714 | 4.5714 | 6.8571 | 4.5714 | 6.8571 | 37.1429
Matt | 12 | 9 | 2022-03-04 | 22.5 | 25.7143 | Total Predicted Work |  | 60 | 2022-03-04 | 3.4286 | 3.8571 | 3.4286 | 3.4286 | 5.1429 | 3.4286 | 5.1429 | 27.8571
Michelle | 8 | 7 | 2022-03-05 | 13.5 | 17.1429 | Expected Work | Actual Work |  | 2022-03-05 | 2.2857 | 2.5714 | 2.2857 | 2.2857 | 3.4286 | 2.2857 | 3.4286 | 18.5714
Tyler | 12 | 9 | 2022-03-06 | 5.5 | 8.5714 | 65 | 59.5 |  | 2022-03-06 | 1.1429 | 1.2857 | 1.1429 | 1.1429 | 1.7143 | 1.1429 | 1.7143 | 9.2857
2022-02-28 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  |  | 2 |  | 2 | 6 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | [5 empty] | 0 | 9 |  | 2022-02-28 | 6 | 9 | 6 | 7 | 10 | 7 | 12 | 57
Hunter |  |  | 2 |  |  | 2 | 6 |  | 2022-03-01 | 3 | 7.5 | 6 | 6 | 8 | 5.5 | 12 | 48
Luke |  |  |  | 1 |  | 1 | 7 |  | 2022-03-02 | 0 | 7.5 | 4 | 5 | 8 | 5 | 10 | 39.5
Matt |  | 2 |  |  | 2 | 2 | 10 |  | 2022-03-03 | -2 | 5 | 2 | 3 | 8 | 4 | 10 | 30
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-03-04 | -2 | 1.5 | 1 | 2 | 7 | 3 | 10 | 22.5
Tyler | [5 empty] | 0 | 12 |  | 2022-03-05 | -3 | 1.5 | 1 | 0 | 5 | 2 | 7 | 13.5
2022-03-01 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-06 | -3 | 1.5 | 0 | 0 | 3 | 1 | 3 | 5.5
Alex |  |  |  | 3 |  | 3 | 3 |  | 2022-03-07 | -3 | 1.5 | 0 | 0 | 3 | 1 | 3 | 5.5
Daniel |  |  |  | 1 | 0.5 | 1.5 | 7.5
Hunter | [5 empty] | 0 | 6
Luke |  |  |  | 1 |  | 1 | 6
Matt |  | 2 |  |  |  | 2 | 8
Michelle |  |  |  | 1.5 |  | 1.5 | 5.5
Tyler | [5 empty] | 0 | 12
2022-03-02 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 3 |  | 3 | 0
Daniel | [5 empty] | 0 | 7.5
Hunter |  |  | 2 |  |  | 2 | 4
Luke |  |  |  | 1 |  | 1 | 5
Matt |  |  |  |  | 3 | 0 | 8
Michelle |  |  |  | 0.5 |  | 0.5 | 5
Tyler |  |  | 1 |  | 1 | 2 | 10
2022-03-03 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 2 |  | 2 | -2
Daniel |  |  |  | 1.5 | 1 | 2.5 | 5
Hunter |  |  | 2 |  |  | 2 | 2
Luke |  |  |  | 2 |  | 2 | 3
Matt | [5 empty] | 0 | 8
Michelle |  |  |  | 1 |  | 1 | 4
Tyler | [5 empty] | 0 | 10
2022-03-04 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | -2
Daniel |  |  |  | 2 | 1.5 | 3.5 | 1.5
Hunter |  |  | 1 |  |  | 1 | 1
Luke |  |  |  | 1 |  | 1 | 2
Matt |  |  | 1 |  |  | 1 | 7
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 10
2022-03-05 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | -3
Daniel | [5 empty] | 0 | 1.5
Hunter | [5 empty] | 0 | 1
Luke |  |  |  | 2 | 0 | 2 | 0
Matt |  |  | 2 |  | 1 | 2 | 5
Michelle |  |  |  | 1 |  | 1 | 2
Tyler |  |  | 1 |  | 2 | 3 | 7
2022-03-06 | Reviews Creation | UM + Unit tests | Login/Signup Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | -3
Daniel | [5 empty] | 0 | 1.5
Hunter |  |  | 1 |  |  | 1 | 0
Luke | [5 empty] | 0 | 0
Matt |  |  | 2 |  |  | 2 | 3
Michelle |  |  |  | 1 |  | 1 | 1
Tyler |  |  | 4 |  | 2 | 4 | 3
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 14
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-02-28 | 8 | -1.7544 | 57 | 57 | 8.1429
2022-03-01 | 9 | 10.5263 | 48 | 48.8571
2022-03-02 | 8.5 | 4.386 | 39.5 | 40.7143
2022-03-03 | 9.5 | 16.6667 | 30 | 32.5714
2022-03-04 | 7.5 | -7.8947 | 22.5 | 24.4286
2022-03-05 | 9 | 10.5263 | 13.5 | 16.2857
2022-03-06 | 8 | -1.7544 | 5.5 | 8.1429
2022-03-07 | 0 | 100 | 5.5 | 0

## Sprint 6
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 5 | 2022-03-07 | 52 | 55 | Connect front end | 14 | 10 | 2022-03-07 | 8 | 10 | 8 | 8 | 12 | 8 | 8 | 62 |  | 0.71429 | 1 | 0.85714 | 1 | 1.1429 | 0.92857 | 0.71429
Daniel | 10 | 9 | 2022-03-08 | 46 | 47.1429 | Create Reviews | 6 | 10 | 2022-03-08 | 6.8571 | 8.5714 | 6.8571 | 6.8571 | 10.2857 | 6.8571 | 6.8571 | 53.1429
Hunter | 8 | 8 | 2022-03-09 | 36 | 39.2857 | Signup page | 8 | 20 | 2022-03-09 | 5.7143 | 7.1429 | 5.7143 | 5.7143 | 8.5714 | 5.7143 | 5.7143 | 44.2857
Luke | 8 | 8 | 2022-03-10 | 25 | 31.4286 | Other | 26 | 15 | 2022-03-10 | 4.5714 | 5.7143 | 4.5714 | 4.5714 | 6.8571 | 4.5714 | 4.5714 | 35.4286
Matt | 12 | 11 | 2022-03-11 | 16 | 23.5714 | Total Predicted Work |  | 55 | 2022-03-11 | 3.4286 | 4.2857 | 3.4286 | 3.4286 | 5.1429 | 3.4286 | 3.4286 | 26.5714
Michelle | 8 | 6.5 | 2022-03-12 | 11 | 15.7143 | Expected Work | Actual Work |  | 2022-03-12 | 2.2857 | 2.8571 | 2.2857 | 2.2857 | 3.4286 | 2.2857 | 2.2857 | 17.7143
Tyler | 8 | 7 | 2022-03-13 | 7.5 | 7.8571 | 62 | 54.5 |  | 2022-03-13 | 1.1429 | 1.4286 | 1.1429 | 1.1429 | 1.7143 | 1.1429 | 1.1429 | 8.8571
2022-03-07 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | 0 | 0 |  | 0 |  | 0 | 8 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  |  |  | 2 | 0.5 | 2 | 8 |  | 2022-03-07 | 8 | 8 | 6 | 7 | 9 | 8 | 6 | 52
Hunter |  |  |  | 2 | 0 | 2 | 6 |  | 2022-03-08 | 8 | 8 | 3 | 6 | 8 | 7 | 6 | 46
Luke |  |  |  | 1 | 0 | 1 | 7 |  | 2022-03-09 | 6 | 6 | 1 | 5 | 6 | 6 | 6 | 36
Matt |  |  | 3 |  |  | 3 | 9 |  | 2022-03-10 | 5 | 4 | 0 | 4 | 3 | 5 | 4 | 25
Michelle |  |  |  |  | 0 | 0 | 8 |  | 2022-03-11 | 4 | 1 | 0 | 3 | 1 | 4 | 3 | 16
Tyler | 2 |  |  |  |  | 2 | 6 |  | 2022-03-12 | 3 | 1 | 0 | 0 | 1 | 3 | 3 | 11
2022-03-08 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-13 | 3 | 1 | 0 | 0 | 1 | 1.5 | 1 | 7.5
Alex | 0 | 0 |  | 0 | 0 | 0 | 8 |  | 2022-03-14 | 3 | 1 | 0 | 0 | 1 | 1.5 | 1 | 7.5
Daniel | [5 empty] | 0 | 8
Hunter | 3 |  |  |  | 1 | 3 | 3
Luke |  |  |  | 1 | 0 | 1 | 6
Matt |  | 1 |  |  | 2 | 1 | 8
Michelle |  |  |  | 1 |  | 1 | 7
Tyler | [5 empty] | 0 | 6
2022-03-09 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 0 | 0 |  | 2 | 0 | 2 | 6
Daniel | 2 |  |  |  | 0.5 | 2 | 6
Hunter | 2 |  |  |  |  | 2 | 1
Luke |  |  |  | 1 |  | 1 | 5
Matt | 2 |  |  |  |  | 2 | 6
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | [5 empty] | 0 | 6
2022-03-10 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 0 | 0 |  | 1 | 1 | 1 | 5
Daniel | 1 |  |  | 1 | 0.5 | 2 | 4
Hunter | 1 |  |  |  |  | 1 | 0
Luke |  |  |  | 1 |  | 1 | 4
Matt |  |  | 3 |  |  | 3 | 3
Michelle |  |  |  | 1 |  | 1 | 5
Tyler |  | 2 |  |  |  | 2 | 4
2022-03-11 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 4
Daniel | 1 |  |  | 1.5 | 0.5 | 3 | 1
Hunter | [5 empty] | 0 | 0
Luke |  |  |  | 1 | 0 | 1 | 3
Matt |  |  | 2 |  |  | 2 | 1
Michelle |  |  |  | 1 |  | 1 | 4
Tyler |  | 1 |  |  |  | 1 | 3
2022-03-12 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 3
Daniel | [5 empty] | 0 | 1
Hunter | [5 empty] | 0 | 0
Luke |  |  |  | 3 | 0 | 3 | 0
Matt | [5 empty] | 0 | 1
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 3
2022-03-13 | Connect front end | Create Reviews | Signup page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 3
Daniel | [5 empty] | 0 | 1
Hunter | [5 empty] | 0 | 0
Luke |  |  |  |  | 0 | 0 | 0
Matt | [5 empty] | 0 | 1
Michelle |  |  |  | 1.5 |  | 1.5 | 1.5
Tyler |  | 2 |  |  |  | 2 | 1
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 6
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-03-07 | 10 | 34.6154 | 52 | 52 | 7.4286
2022-03-08 | 6 | -19.2308 | 46 | 44.5714
2022-03-09 | 10 | 34.6154 | 36 | 37.1429
2022-03-10 | 11 | 48.0769 | 25 | 29.7143
2022-03-11 | 9 | 21.1538 | 16 | 22.2857
2022-03-12 | 5 | -32.6923 | 11 | 14.8571
2022-03-13 | 3.5 | -52.8846 | 7.5 | 7.4286
2022-03-14 | 0 | 100 | 7.5 | 0

## Sprint 7
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 8 | 2022-03-14 | 53 | 55 | Document Update | 12.5 | 15 | 2022-03-14 | 8 | 9 | 8 | 8 | 12 | 8 | 8 | 61 |  | 1.1429 | 1 | 0.85714 | 0.85714 | 1.2857 | 0.92857 | 1
Daniel | 9 | 9 | 2022-03-15 | 42.5 | 47.1429 | Code Updates | 18 | 20 | 2022-03-15 | 6.8571 | 7.7143 | 6.8571 | 6.8571 | 10.2857 | 6.8571 | 6.8571 | 52.2857
Hunter | 8 | 8 | 2022-03-16 | 32.5 | 39.2857 | Food Flag Back end | 6 | 10 | 2022-03-16 | 5.7143 | 6.4286 | 5.7143 | 5.7143 | 8.5714 | 5.7143 | 5.7143 | 43.5714
Luke | 8 | 6 | 2022-03-17 | 24.5 | 31.4286 | Other | 21 | 10 | 2022-03-17 | 4.5714 | 5.1429 | 4.5714 | 4.5714 | 6.8571 | 4.5714 | 4.5714 | 34.8571
Matt | 12 | 12 | 2022-03-18 | 14 | 23.5714 | Total Predicted Work |  | 55 | 2022-03-18 | 3.4286 | 3.8571 | 3.4286 | 3.4286 | 5.1429 | 3.4286 | 3.4286 | 26.1429
Michelle | 8 | 6.5 | 2022-03-19 | 9 | 15.7143 | Expected Work | Actual Work |  | 2022-03-19 | 2.2857 | 2.5714 | 2.2857 | 2.2857 | 3.4286 | 2.2857 | 2.2857 | 17.4286
Tyler | 8 | 8 | 2022-03-20 | 3.5 | 7.8571 | 61 | 57.5 |  | 2022-03-20 | 1.1429 | 1.2857 | 1.1429 | 1.1429 | 1.7143 | 1.1429 | 1.1429 | 8.7143
2022-03-14 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | 0 | 0 |  | 0 |  | 0 | 8 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  |  |  | 2 | 0 | 2 | 7 |  | 2022-03-14 | 8 | 7 | 6 | 8 | 9 | 8 | 7 | 53
Hunter |  |  |  | 2 | 0 | 2 | 6 |  | 2022-03-15 | 8 | 5.5 | 3 | 5 | 7 | 7 | 7 | 42.5
Luke |  |  |  |  | 0 | 0 | 8 |  | 2022-03-16 | 6 | 3.5 | 3 | 5 | 4 | 6 | 5 | 32.5
Matt |  |  | 3 |  |  | 3 | 9 |  | 2022-03-17 | 5 | 2.5 | 2 | 5 | 2 | 5 | 3 | 24.5
Michelle |  |  |  |  | 0 | 0 | 8 |  | 2022-03-18 | 2 | 0 | 2 | 4 | 0 | 4 | 2 | 14
Tyler |  | 1 |  |  |  | 1 | 7 |  | 2022-03-19 | 1 | 0 | 0 | 3 | 0 | 3 | 2 | 9
2022-03-15 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-20 | 0 | 0 | 0 | 2 | 0 | 1.5 | 0 | 3.5
Alex | 0 | 0 |  | 0 | 0 | 0 | 8 |  | 2022-03-21 | 0 | 0 | 0 | 2 | 0 | 1.5 | 0 | 3.5
Daniel | 1.5 |  |  |  | 1 | 1.5 | 5.5
Hunter |  | 3 |  |  | 1 | 3 | 3
Luke |  |  |  | 3 | 0 | 3 | 5
Matt |  |  | 2 |  |  | 2 | 7
Michelle |  |  |  | 1 |  | 1 | 7
Tyler | [5 empty] | 0 | 7
2022-03-16 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 | 0 |  |  | 0 | 2 | 6
Daniel | 2 |  |  |  | 0.5 | 2 | 3.5
Hunter | [5 empty] | 0 | 3
Luke | [5 empty] | 0 | 5
Matt |  |  | 1 | 2 |  | 3 | 4
Michelle |  |  |  | 1 |  | 1 | 6
Tyler |  | 2 |  |  |  | 2 | 5
2022-03-17 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 1 | 0 |  |  | 1 | 1 | 5
Daniel | 1 |  |  |  | 0.5 | 1 | 2.5
Hunter |  | 1 |  |  |  | 1 | 2
Luke | [5 empty] | 0 | 5
Matt |  | 2 |  |  |  | 2 | 2
Michelle |  |  |  | 1 |  | 1 | 5
Tyler |  | 2 |  |  |  | 2 | 3
2022-03-18 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 |  |  | 1 |  | 3 | 2
Daniel | 1 |  |  | 1.5 |  | 2.5 | 0
Hunter | [5 empty] | 0 | 2
Luke |  |  |  | 1 | 0 | 1 | 4
Matt |  | 2 |  |  |  | 2 | 0
Michelle |  |  |  | 1 |  | 1 | 4
Tyler |  | 1 |  |  |  | 1 | 2
2022-03-19 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 1 |  |  |  |  | 1 | 1
Daniel | [5 empty] | 0 | 0
Hunter |  | 2 |  |  |  | 2 | 0
Luke |  |  |  | 1 | 0 | 1 | 3
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 2
2022-03-20 | Document Update | Code Updates | Food Flag Back end | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 1 |  |  |  |  | 1 | 0
Daniel | [5 empty] | 0 | 0
Hunter | [5 empty] | 0 | 0
Luke |  |  |  | 1 | 0 | 1 | 2
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1.5 |  | 1.5 | 1.5
Tyler |  | 2 |  |  |  | 2 | 0
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 4
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-03-14 | 8 | 5.6604 | 53 | 53 | 7.5714
2022-03-15 | 10.5 | 38.6792 | 42.5 | 45.4286
2022-03-16 | 10 | 32.0755 | 32.5 | 37.8571
2022-03-17 | 8 | 5.6604 | 24.5 | 30.2857
2022-03-18 | 10.5 | 38.6792 | 14 | 22.7143
2022-03-19 | 5 | -33.9623 | 9 | 15.1429
2022-03-20 | 5.5 | -27.3585 | 3.5 | 7.5714
2022-03-21 | 0 | 100 | 3.5 | 0

## Sprint 8
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 2 | 2022-03-21 | 55 | 54 | Front End Structure | 6 | 15 | 2022-03-21 | 8 | 8 | 8 | 12 | 12 | 8 | 8 | 64 |  | 0.28571 | 0.78571 | 0.71429 | 1 | 1.5714 | 0.78571 | 0.57143
Daniel | 8 | 6.5 | 2022-03-22 | 47.5 | 46.2857 | Code/Unit Test Refactor | 18 | 20 | 2022-03-22 | 6.8571 | 6.8571 | 6.8571 | 10.2857 | 10.2857 | 6.8571 | 6.8571 | 54.8571
Hunter | 8 | 6 | 2022-03-23 | 42.5 | 38.5714 | Updated DB keys | 1 | 4 | 2022-03-23 | 5.7143 | 5.7143 | 5.7143 | 8.5714 | 8.5714 | 5.7143 | 5.7143 | 45.7143
Luke | 12 | 8 | 2022-03-24 | 38.5 | 30.8571 | Other | 22.5 | 15 | 2022-03-24 | 4.5714 | 4.5714 | 4.5714 | 6.8571 | 6.8571 | 4.5714 | 4.5714 | 36.5714
Matt | 12 | 14 | 2022-03-25 | 31.5 | 23.1429 | Total Predicted Work |  | 54 | 2022-03-25 | 3.4286 | 3.4286 | 3.4286 | 5.1429 | 5.1429 | 3.4286 | 3.4286 | 27.4286
Michelle | 8 | 6.5 | 2022-03-26 | 24.5 | 15.4286 | Expected Work | Actual Work |  | 2022-03-26 | 2.2857 | 2.2857 | 2.2857 | 3.4286 | 3.4286 | 2.2857 | 2.2857 | 18.2857
Tyler | 8 | 6 | 2022-03-27 | 15 | 7.7143 | 64 | 49 |  | 2022-03-27 | 1.1429 | 1.1429 | 1.1429 | 1.7143 | 1.7143 | 1.1429 | 1.1429 | 9.1429
2022-03-21 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | [5 empty] | 0 | 8 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  |  |  | 1 | 0.5 | 1 | 7 |  | 2022-03-21 | 8 | 7 | 7 | 11 | 9 | 7 | 6 | 55
Hunter |  | 1 |  |  |  | 1 | 7 |  | 2022-03-22 | 8 | 7 | 5 | 10 | 7 | 5.5 | 5 | 47.5
Luke |  |  |  | 1 |  | 1 | 11 |  | 2022-03-23 | 6 | 5 | 5 | 10 | 7 | 4.5 | 5 | 42.5
Matt |  | 2 |  | 1 |  | 3 | 9 |  | 2022-03-24 | 6 | 5 | 5 | 10 | 4 | 3.5 | 5 | 38.5
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-03-25 | 6 | 1.5 | 3 | 10 | 4 | 3 | 4 | 31.5
Tyler | 2 |  |  |  |  | 2 | 6 |  | 2022-03-26 | 6 | 1.5 | 3 | 7 | 1 | 2 | 4 | 24.5
2022-03-22 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-03-27 | 6 | 1.5 | 2 | 4 | -2 | 1.5 | 2 | 15
Alex |  |  |  |  | 0 | 0 | 8 |  | 2022-03-28 | 6 | 1.5 | 2 | 4 | -2 | 1.5 | 2 | 15
Daniel | [5 empty] | 0 | 7
Hunter |  | 2 |  |  | 1 | 2 | 5
Luke |  |  |  | 1 | 0 | 1 | 10
Matt |  | 2 |  |  |  | 2 | 7
Michelle |  |  |  | 1.5 |  | 1.5 | 5.5
Tyler | 1 |  |  |  |  | 1 | 5
2022-03-23 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 2 | 0 | 2 | 6
Daniel |  |  | 1 | 1 | 0.5 | 2 | 5
Hunter | [5 empty] | 0 | 5
Luke | [5 empty] | 0 | 10
Matt | [5 empty] | 0 | 7
Michelle |  |  |  | 1 |  | 1 | 4.5
Tyler | [5 empty] | 0 | 5
2022-03-24 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  |  | 1 | 0 | 6
Daniel |  |  |  |  | 0.5 | 0 | 5
Hunter | [5 empty] | 0 | 5
Luke | [5 empty] | 0 | 10
Matt |  | 3 |  |  |  | 3 | 4
Michelle |  |  |  | 1 |  | 1 | 3.5
Tyler | [5 empty] | 0 | 5
2022-03-25 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 6
Daniel |  |  |  | 2 | 1.5 | 3.5 | 1.5
Hunter |  | 2 |  |  |  | 2 | 3
Luke | [5 empty] | 0 | 10
Matt | [5 empty] | 0 | 4
Michelle |  |  |  | 0.5 |  | 0.5 | 3
Tyler | 1 |  |  |  |  | 1 | 4
2022-03-26 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 6
Daniel | [5 empty] | 0 | 1.5
Hunter | [5 empty] | 0 | 3
Luke |  |  |  | 3 | 0 | 3 | 7
Matt |  | 2 |  | 1 |  | 3 | 1
Michelle |  |  |  | 1 |  | 1 | 2
Tyler | [5 empty] | 0 | 4
2022-03-27 | Front End Structure | Code/Unit Test Refactor | Updated DB keys | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 6
Daniel | [5 empty] | 0 | 1.5
Hunter |  | 1 |  |  |  | 1 | 2
Luke |  |  |  | 3 | 0 | 3 | 4
Matt |  | 3 |  |  |  | 3 | -2
Michelle |  |  |  | 0.5 |  | 0.5 | 1.5
Tyler | 2 |  |  |  |  | 2 | 2
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 5
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-03-21 | 9 | 14.5455 | 55 | 55 | 7.8571
2022-03-22 | 7.5 | -4.5455 | 47.5 | 47.1429
2022-03-23 | 5 | -36.3636 | 42.5 | 39.2857
2022-03-24 | 4 | -49.0909 | 38.5 | 31.4286
2022-03-25 | 7 | -10.9091 | 31.5 | 23.5714
2022-03-26 | 7 | -10.9091 | 24.5 | 15.7143
2022-03-27 | 9.5 | 20.9091 | 15 | 7.8571
2022-03-28 | 0 | 100 | 15 | 0

## Sprint 9
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 16 | 9 | 2022-03-28 | 65.5 | 66 | Sign up and SIgn in | 15 | 18 | 2022-03-28 | 16 | 14 | 8 | 10 | 16 | 8 | 8 | 80 |  | 1 | 0.85714 | 0.57143 | 1.1429 | 1.7143 | 0.5 | 0.57143
Daniel | 14 | 9 | 2022-03-29 | 55 | 56.5714 | Scan | 12 | 20 | 2022-03-29 | 13.7143 | 12 | 6.8571 | 8.5714 | 13.7143 | 6.8571 | 6.8571 | 68.5714
Hunter | 8 | 6 | 2022-03-30 | 49 | 47.1429 | Logging Refactor | 8 | 16 | 2022-03-30 | 11.4286 | 10 | 5.7143 | 7.1429 | 11.4286 | 5.7143 | 5.7143 | 57.1429
Luke | 10 | 10 | 2022-03-31 | 42 | 37.7143 | Other | 24 | 12 | 2022-03-31 | 9.1429 | 8 | 4.5714 | 5.7143 | 9.1429 | 4.5714 | 4.5714 | 45.7143
Matt | 16 | 15 | 2022-04-01 | 34 | 28.2857 | Total Predicted Work |  | 66 | 2022-04-01 | 6.8571 | 6 | 3.4286 | 4.2857 | 6.8571 | 3.4286 | 3.4286 | 34.2857
Michelle | 8 | 4 | 2022-04-02 | 28 | 18.8571 | Expected Work | Actual Work |  | 2022-04-02 | 4.5714 | 4 | 2.2857 | 2.8571 | 4.5714 | 2.2857 | 2.2857 | 22.8571
Tyler | 8 | 6 | 2022-04-03 | 21 | 9.4286 | 80 | 59 |  | 2022-04-03 | 2.2857 | 2 | 1.1429 | 1.4286 | 2.2857 | 1.1429 | 1.1429 | 11.4286
2022-03-28 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  | 2 |  | 2 | 2 | 14 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  | 3 |  |  | 1 | 3 | 11 |  | 2022-03-28 | 14 | 11 | 6 | 8 | 13 | 7.5 | 6 | 65.5
Hunter |  |  |  | 2 |  | 2 | 6 |  | 2022-03-29 | 11 | 9 | 6 | 6 | 10 | 7 | 6 | 55
Luke |  |  |  | 2 |  | 2 | 8 |  | 2022-03-30 | 11 | 9 | 4 | 6 | 8 | 7 | 4 | 49
Matt | 3 |  |  |  |  | 3 | 13 |  | 2022-03-31 | 9 | 6.5 | 4 | 6 | 6 | 6.5 | 4 | 42
Michelle |  |  |  | 0.5 |  | 0.5 | 7.5 |  | 2022-04-01 | 7 | 5 | 4 | 3 | 6 | 6 | 3 | 34
Tyler | 2 |  |  |  |  | 2 | 6 |  | 2022-04-02 | 7 | 5 | 3 | 1 | 4 | 5 | 3 | 28
2022-03-29 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-03 | 7 | 5 | 2 | 0 | 1 | 4 | 2 | 21
Alex |  |  | 3 |  | 2 | 3 | 11 |  | 2022-04-04 | 7 | 5 | 2 | 0 | 1 | 4 | 2 | 21
Daniel |  | 2 |  |  | 0.5 | 2 | 9
Hunter | [5 empty] | 0 | 6
Luke |  |  |  | 2 |  | 2 | 6
Matt | 2 |  |  | 1 |  | 3 | 10
Michelle |  |  |  | 0.5 |  | 0.5 | 7
Tyler | [5 empty] | 0 | 6
2022-03-30 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 0 |  |  | 0 | 11
Daniel | [5 empty] | 0 | 9
Hunter |  |  |  | 2 |  | 2 | 4
Luke | [5 empty] | 0 | 6
Matt | 2 |  |  |  |  | 2 | 8
Michelle |  |  |  | 0 |  | 0 | 7
Tyler | 2 |  |  |  |  | 2 | 4
2022-03-31 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 1 | 1 |  | 2 | 9
Daniel |  | 2.5 |  |  | 1 | 2.5 | 6.5
Hunter | [5 empty] | 0 | 4
Luke | [5 empty] | 0 | 6
Matt |  |  |  | 2 |  | 2 | 6
Michelle |  |  |  | 0.5 |  | 0.5 | 6.5
Tyler | [5 empty] | 0 | 4
2022-04-01 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 2 |  |  | 2 | 7
Daniel |  | 1.5 |  |  | 2 | 1.5 | 5
Hunter | [5 empty] | 0 | 4
Luke |  |  |  | 3 |  | 3 | 3
Matt | [5 empty] | 0 | 6
Michelle |  |  |  | 0.5 |  | 0.5 | 6
Tyler | 1 |  |  |  |  | 1 | 3
2022-04-02 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 0 |  |  | 0 | 7
Daniel | [5 empty] | 0 | 5
Hunter |  |  |  | 1 |  | 1 | 3
Luke |  |  |  | 2 |  | 2 | 1
Matt | 2 |  |  |  |  | 2 | 4
Michelle |  |  |  | 1 |  | 1 | 5
Tyler | [5 empty] | 0 | 3
2022-04-03 | Sign up and SIgn in | Scan | Logging Refactor | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 0 |  |  | 0 | 7
Daniel | [5 empty] | 0 | 5
Hunter |  |  |  | 1 |  | 1 | 2
Luke |  |  |  | 1 |  | 1 | 0
Matt |  | 3 |  |  |  | 3 | 1
Michelle |  |  |  | 1 |  | 1 | 4
Tyler | 1 |  |  |  |  | 1 | 2
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 8.5
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-03-28 | 14.5 | 54.9618 | 65.5 | 65.5 | 9.3571
2022-03-29 | 10.5 | 12.2137 | 55 | 56.1429
2022-03-30 | 6 | -35.8779 | 49 | 46.7857
2022-03-31 | 7 | -25.1908 | 42 | 37.4286
2022-04-01 | 8 | -14.5038 | 34 | 28.0714
2022-04-02 | 6 | -35.8779 | 28 | 18.7143
2022-04-03 | 7 | -25.1908 | 21 | 9.3571
2022-04-04 | 0 | 100 | 21 | 0

## Sprint 10
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 8 | 6 | 2022-04-04 | 68 | 60 | Food Info Page | 19 | 20 | 2022-04-04 | 8 | 18 | 10 | 6 | 16 | 8 | 8 | 74 |  | 0.71429 | 2.3571 | 0.85714 | 0.57143 | 1.8571 | 0.71429 | 0.85714
Daniel | 18 | 16.5 | 2022-04-05 | 62 | 51.4286 | Flags Page | 10 | 10 | 2022-04-05 | 6.8571 | 15.4286 | 8.5714 | 5.1429 | 13.7143 | 6.8571 | 6.8571 | 63.4286
Hunter | 10 | 8 | 2022-04-06 | 51.5 | 42.8571 | Add Product Page | 14.5 | 15 | 2022-04-06 | 5.7143 | 12.8571 | 7.1429 | 4.2857 | 11.4286 | 5.7143 | 5.7143 | 52.8571
Luke | 6 | 4 | 2022-04-07 | 45.5 | 34.2857 | Other | 18 | 15 | 2022-04-07 | 4.5714 | 10.2857 | 5.7143 | 3.4286 | 9.1429 | 4.5714 | 4.5714 | 42.2857
Matt | 16 | 15 | 2022-04-08 | 38.5 | 25.7143 | Total Predicted Work |  | 60 | 2022-04-08 | 3.4286 | 7.7143 | 4.2857 | 2.5714 | 6.8571 | 3.4286 | 3.4286 | 31.7143
Michelle | 8 | 6 | 2022-04-09 | 29.5 | 17.1429 | Expected Work | Actual Work |  | 2022-04-09 | 2.2857 | 5.1429 | 2.8571 | 1.7143 | 4.5714 | 2.2857 | 2.2857 | 21.1429
Tyler | 8 | 6 | 2022-04-10 | 12.5 | 8.5714 | 74 | 61.5 |  | 2022-04-10 | 1.1429 | 2.5714 | 1.4286 | 0.85714 | 2.2857 | 1.1429 | 1.1429 | 10.5714
2022-04-04 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  |  | 1 |  | 1 | 7 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | [5 empty] | 0 | 18 |  | 2022-04-04 | 7 | 18 | 8 | 6 | 14 | 7 | 8 | 68
Hunter | 2 |  |  |  |  | 2 | 8 |  | 2022-04-05 | 7 | 16 | 7 | 6 | 12 | 6 | 8 | 62
Luke | [5 empty] | 0 | 6 |  | 2022-04-06 | 5 | 16 | 5 | 5 | 9 | 5.5 | 6 | 51.5
Matt | 2 |  |  |  |  | 2 | 14 |  | 2022-04-07 | 5 | 13.5 | 4 | 5 | 7 | 5 | 6 | 45.5
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-04-08 | 5 | 11.5 | 4 | 3 | 5 | 4 | 6 | 38.5
Tyler | [5 empty] | 0 | 8 |  | 2022-04-09 | 4 | 8.5 | 4 | 3 | 3 | 3 | 4 | 29.5
2022-04-05 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-10 | 2 | 1.5 | 2 | 2 | 1 | 2 | 2 | 12.5
Alex |  |  |  | 0 |  | 0 | 7 |  | 2022-04-11 | 2 | 1.5 | 2 | 2 | 1 | 2 | 2 | 12.5
Daniel |  |  | 2 |  | 0.5 | 2 | 16
Hunter | 1 |  |  |  |  | 1 | 7
Luke | [5 empty] | 0 | 6
Matt | 2 |  |  |  |  | 2 | 12
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | [5 empty] | 0 | 8
2022-04-06 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 2 |  | 2 | 5
Daniel | [5 empty] | 0 | 16
Hunter | 2 |  |  |  |  | 2 | 5
Luke |  |  |  | 1 |  | 1 | 5
Matt | 1 | 2 |  |  |  | 3 | 9
Michelle |  |  |  | 0.5 |  | 0.5 | 5.5
Tyler | 2 |  |  |  |  | 2 | 6
2022-04-07 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 0 |  | 0 | 5
Daniel |  |  | 2.5 |  | 1 | 2.5 | 13.5
Hunter | 1 |  |  |  |  | 1 | 4
Luke | [5 empty] | 0 | 5
Matt |  | 2 |  |  |  | 2 | 7
Michelle |  |  |  | 0.5 |  | 0.5 | 5
Tyler | [5 empty] | 0 | 6
2022-04-08 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 0 |  | 0 | 5
Daniel |  |  | 2 |  | 1 | 2 | 11.5
Hunter | [5 empty] | 0 | 4
Luke |  |  |  | 2 |  | 2 | 3
Matt |  | 2 |  |  |  | 2 | 5
Michelle |  |  |  | 1 |  | 1 | 4
Tyler | [5 empty] | 0 | 6
2022-04-09 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 4
Daniel |  |  | 3 |  | 2 | 3 | 8.5
Hunter | [5 empty] | 0 | 4
Luke | [5 empty] | 0 | 3
Matt |  | 2 |  |  |  | 2 | 3
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | 2 |  |  |  |  | 2 | 4
2022-04-10 | Food Info Page | Flags Page | Add Product Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 2 |  | 2 | 2
Daniel |  |  | 5 | 2 |  | 7 | 1.5
Hunter | 2 |  |  |  |  | 2 | 2
Luke |  |  |  | 1 |  | 1 | 2
Matt |  | 2 |  |  |  | 2 | 1
Michelle |  |  |  | 1 |  | 1 | 2
Tyler | 2 |  |  |  |  | 2 | 2
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 4.5
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-04-04 | 6 | -38.2353 | 68 | 68 | 9.7143
2022-04-05 | 6 | -38.2353 | 62 | 58.2857
2022-04-06 | 10.5 | 8.0882 | 51.5 | 48.5714
2022-04-07 | 6 | -38.2353 | 45.5 | 38.8571
2022-04-08 | 7 | -27.9412 | 38.5 | 29.1429
2022-04-09 | 9 | -7.3529 | 29.5 | 19.4286
2022-04-10 | 17 | 75 | 12.5 | 9.7143
2022-04-11 | 0 | 100 | 12.5 | 0

## Sprint 11
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 10 | 9 | 2022-04-11 | 58 | 94 | Individual Feature Work | 48.5 | 50 | 2022-04-11 | 10 | 10 | 10 | 6 | 16 | 8 | 8 | 68 |  | 0.85714 | 1.6429 | 0.85714 | 0.71429 | 2.2857 | 1.4286 | 0.71429
Daniel | 10 | 11.5 | 2022-04-12 | 45.5 | 80.5714 | Logging | 9 | 14 | 2022-04-12 | 8.5714 | 8.5714 | 8.5714 | 5.1429 | 13.7143 | 6.8571 | 6.8571 | 58.2857
Hunter | 10 | 10 | 2022-04-13 | 37 | 67.1429 | Food Info Page | 7 | 15 | 2022-04-13 | 7.1429 | 7.1429 | 7.1429 | 4.2857 | 11.4286 | 5.7143 | 5.7143 | 48.5714
Luke | 6 | 5 | 2022-04-14 | 27 | 53.7143 | Other | 5 | 15 | 2022-04-14 | 5.7143 | 5.7143 | 5.7143 | 3.4286 | 9.1429 | 4.5714 | 4.5714 | 38.8571
Matt | 16 | 16 | 2022-04-15 | 19 | 40.2857 | Total Predicted Work |  | 94 | 2022-04-15 | 4.2857 | 4.2857 | 4.2857 | 2.5714 | 6.8571 | 3.4286 | 3.4286 | 29.1429
Michelle | 8 | 11 | 2022-04-16 | 9.5 | 26.8571 | Expected Work | Actual Work |  | 2022-04-16 | 2.8571 | 2.8571 | 2.8571 | 1.7143 | 4.5714 | 2.2857 | 2.2857 | 19.4286
Tyler | 8 | 7 | 2022-04-17 | -1.5 | 13.4286 | 68 | 69.5 |  | 2022-04-17 | 1.4286 | 1.4286 | 1.4286 | 0.85714 | 2.2857 | 1.1429 | 1.1429 | 9.7143
2022-04-11 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  | 3 |  |  |  | 3 | 7 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | [5 empty] | 0 | 10 |  | 2022-04-11 | 7 | 10 | 6 | 6 | 16 | 7 | 6 | 58
Hunter | 4 |  |  |  |  | 4 | 6 |  | 2022-04-12 | 7 | 6 | 4 | 5 | 12 | 5.5 | 6 | 45.5
Luke | [5 empty] | 0 | 6 |  | 2022-04-13 | 7 | 5 | 4 | 4 | 10 | 4 | 3 | 37
Matt | [5 empty] | 0 | 16 |  | 2022-04-14 | 5 | 2 | 3 | 3 | 10 | 2 | 2 | 27
Michelle | 1 |  |  |  |  | 1 | 7 |  | 2022-04-15 | 5 | 2 | 1 | 2 | 7 | 0 | 2 | 19
Tyler |  |  | 2 |  |  | 2 | 6 |  | 2022-04-16 | 3 | -0.5 | 1 | 1 | 5 | -2 | 2 | 9.5
2022-04-12 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-17 | 1 | -1.5 | 0 | 1 | 0 | -3 | 1 | -1.5
Alex |  | 0 |  |  |  | 0 | 7 |  | 2022-04-18 | 1 | -1.5 | 0 | 1 | 0 | -3 | 1 | -1.5
Daniel | 4 |  |  |  | 2 | 4 | 6
Hunter | 2 |  |  |  |  | 2 | 4
Luke |  |  |  | 1 |  | 1 | 5
Matt | 4 |  |  |  |  | 4 | 12
Michelle | 1.5 |  |  |  |  | 1.5 | 5.5
Tyler | [5 empty] | 0 | 6
2022-04-13 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 0 |  |  |  | 0 | 7
Daniel | 1 |  |  |  |  | 1 | 5
Hunter | [5 empty] | 0 | 4
Luke |  |  |  | 1 |  | 1 | 4
Matt | 2 |  |  |  |  | 2 | 10
Michelle | 1.5 |  |  |  |  | 1.5 | 4
Tyler |  |  | 3 |  |  | 3 | 3
2022-04-14 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 2 |  |  |  | 2 | 5
Daniel | 3 |  |  |  | 1 | 3 | 2
Hunter | 1 |  |  |  |  | 1 | 3
Luke |  |  |  | 1 |  | 1 | 3
Matt | [5 empty] | 0 | 10
Michelle | 2 |  |  |  |  | 2 | 2
Tyler |  |  | 1 |  |  | 1 | 2
2022-04-15 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 0 |  |  |  | 0 | 5
Daniel | [5 empty] | 0 | 2
Hunter | 2 |  |  |  |  | 2 | 1
Luke |  |  |  | 1 |  | 1 | 2
Matt | 3 |  |  |  |  | 3 | 7
Michelle | 2 |  |  |  |  | 2 | 0
Tyler | [5 empty] | 0 | 2
2022-04-16 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 2 |  |  |  | 2 | 3
Daniel | 2.5 |  |  |  | 0.5 | 2.5 | -0.5
Hunter | [5 empty] | 0 | 1
Luke |  |  |  | 1 |  | 1 | 1
Matt | 2 |  |  |  |  | 2 | 5
Michelle | 2 |  |  |  |  | 2 | -2
Tyler | [5 empty] | 0 | 2
2022-04-17 | Individual Feature Work | Logging | Food Info Page | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 2 |  |  |  | 2 | 1
Daniel | 1 |  |  |  |  | 1 | -1.5
Hunter | 1 |  |  |  |  | 1 | 0
Luke | [5 empty] | 0 | 1
Matt | 5 |  |  |  |  | 5 | 0
Michelle | 1 |  |  |  |  | 1 | -3
Tyler |  |  | 1 |  |  | 1 | 1
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 3.5
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-04-11 | 10 | 20.6897 | 58 | 58 | 8.2857
2022-04-12 | 12.5 | 50.8621 | 45.5 | 49.7143
2022-04-13 | 8.5 | 2.5862 | 37 | 41.4286
2022-04-14 | 10 | 20.6897 | 27 | 33.1429
2022-04-15 | 8 | -3.4483 | 19 | 24.8571
2022-04-16 | 9.5 | 14.6552 | 9.5 | 16.5714
2022-04-17 | 11 | 32.7586 | -1.5 | 8.2857
2022-04-18 | 0 | 100 | -1.5 | 0

## Sprint 12
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 10 | 15 | 2022-04-18 | 67 | 60 | Individual Feature Work | 65.5 | 40 | 2022-04-18 | 10 | 20 | 10 | 9 | 16 | 8 | 8 | 81 |  | 1.7143 | 3.8571 | 1.1429 | 1.1429 | 1.1429 | 1.0714 | 1.1429
Daniel | 20 | 30 | 2022-04-19 | 56 | 51.4286 | Hosting/Production Environment | 19 | 5 | 2022-04-19 | 8.5714 | 17.1429 | 8.5714 | 7.7143 | 13.7143 | 6.8571 | 6.8571 | 69.4286
Hunter | 10 | 10 | 2022-04-20 | 48 | 42.8571 | Logging | 7 | 10 | 2022-04-20 | 7.1429 | 14.2857 | 7.1429 | 6.4286 | 11.4286 | 5.7143 | 5.7143 | 57.8571
Luke | 9 | 9 | 2022-04-21 | 35.5 | 34.2857 | Other | 1 | 5 | 2022-04-21 | 5.7143 | 11.4286 | 5.7143 | 5.1429 | 9.1429 | 4.5714 | 4.5714 | 46.2857
Matt | 16 | 12 | 2022-04-22 | 22 | 25.7143 | Total Predicted Work |  | 60 | 2022-04-22 | 4.2857 | 8.5714 | 4.2857 | 3.8571 | 6.8571 | 3.4286 | 3.4286 | 34.7143
Michelle | 8 | 8.5 | 2022-04-23 | 7 | 17.1429 | Expected Work | Actual Work |  | 2022-04-23 | 2.8571 | 5.7143 | 2.8571 | 2.5714 | 4.5714 | 2.2857 | 2.2857 | 23.1429
Tyler | 8 | 8 | 2022-04-24 | -11.5 | 8.5714 | 81 | 92.5 |  | 2022-04-24 | 1.4286 | 2.8571 | 1.4286 | 1.2857 | 2.2857 | 1.1429 | 1.1429 | 11.5714
2022-04-18 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  |  | 2 | 1 |  | 3 | 7 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | 1 | 2 |  |  | 1 | 3 | 17 |  | 2022-04-18 | 7 | 17 | 8 | 8 | 12 | 7 | 8 | 67
Hunter | 2 |  |  |  |  | 2 | 8 |  | 2022-04-19 | 4 | 15 | 8 | 7 | 8 | 6 | 8 | 56
Luke | 1 |  |  |  |  | 1 | 8 |  | 2022-04-20 | 2 | 15 | 8 | 6 | 4 | 5 | 8 | 48
Matt | 4 |  |  |  |  | 4 | 12 |  | 2022-04-21 | 0 | 9 | 8 | 4 | 4 | 4.5 | 6 | 35.5
Michelle | 1 |  |  |  |  | 1 | 7 |  | 2022-04-22 | -1 | 2.5 | 6 | 3 | 4 | 2.5 | 5 | 22
Tyler | [5 empty] | 0 | 8 |  | 2022-04-23 | -3 | -3 | 3 | 2 | 4 | 1 | 3 | 7
2022-04-19 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-04-24 | -5 | -10 | 0 | 0 | 4 | -0.5 | 0 | -11.5
Alex |  |  | 3 |  |  | 3 | 4 |  | 2022-04-25 | -5 | -10 | 0 | 0 | 4 | -0.5 | 0 | -11.5
Daniel | 2 |  |  |  | 0.5 | 2 | 15
Hunter | [5 empty] | 0 | 8
Luke | 1 |  |  |  |  | 1 | 7
Matt | 4 |  |  |  |  | 4 | 8
Michelle | 1 |  |  |  |  | 1 | 6
Tyler | [5 empty] | 0 | 8
2022-04-20 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  | 2 |  |  | 2 | 2
Daniel | [5 empty] | 0 | 15
Hunter | [5 empty] | 0 | 8
Luke | 1 |  |  |  |  | 1 | 6
Matt | 4 |  |  |  |  | 4 | 4
Michelle | 1 |  |  |  |  | 1 | 5
Tyler | [5 empty] | 0 | 8
2022-04-21 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 |  |  |  |  | 2 | 0
Daniel |  | 6 |  |  | 1 | 6 | 9
Hunter | [5 empty] | 0 | 8
Luke | 2 |  |  |  |  | 2 | 4
Matt | [5 empty] | 0 | 4
Michelle | 0.5 |  |  |  |  | 0.5 | 4.5
Tyler | 2 |  |  |  |  | 2 | 6
2022-04-22 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 1 |  |  |  |  | 1 | -1
Daniel |  | 6.5 |  |  | 1.5 | 6.5 | 2.5
Hunter | 2 |  |  |  |  | 2 | 6
Luke | 1 |  |  |  |  | 1 | 3
Matt | [5 empty] | 0 | 4
Michelle | 2 |  |  |  |  | 2 | 2.5
Tyler | 1 |  |  |  |  | 1 | 5
2022-04-23 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 |  |  |  |  | 2 | -3
Daniel | 2 | 3.5 |  |  |  | 5.5 | -3
Hunter | 3 |  |  |  |  | 3 | 3
Luke | 1 |  |  |  |  | 1 | 2
Matt | [5 empty] | 0 | 4
Michelle | 1.5 |  |  |  |  | 1.5 | 1
Tyler | 2 |  |  |  |  | 2 | 3
2022-04-24 | Individual Feature Work | Hosting/Production Environment | Logging | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 |  |  |  |  | 2 | -5
Daniel | 6 | 1 |  |  |  | 7 | -10
Hunter | 3 |  |  |  |  | 3 | 0
Luke | 2 |  |  |  |  | 2 | 0
Matt | [5 empty] | 0 | 4
Michelle | 1.5 |  |  |  |  | 1.5 | -0.5
Tyler | 3 |  |  |  |  | 3 | 0
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 4
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-04-18 | 14 | 46.2687 | 67 | 67 | 9.5714
2022-04-19 | 11 | 14.9254 | 56 | 57.4286
2022-04-20 | 8 | -16.4179 | 48 | 47.8571
2022-04-21 | 12.5 | 30.597 | 35.5 | 38.2857
2022-04-22 | 13.5 | 41.0448 | 22 | 28.7143
2022-04-23 | 15 | 56.7164 | 7 | 19.1429
2022-04-24 | 18.5 | 93.2836 | -11.5 | 9.5714
2022-04-25 | 0 | 100 | -11.5 | 0

## Sprint 13
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 10 | 8 | 2022-04-25 | 39 | 43 | Individual Feature Work | 42 | 30 | 2022-04-25 | 10 | 10 | 10 | 9 | 0 | 8 | 8 | 55 |  | 1.1429 | 0.85714 | 1.5714 | 1.2857 | 0 | 0.85714 | 0
Daniel | 10 | 11 | 2022-04-26 | 27 | 36.8571 | Hosting/Production Environment | 6.5 | 5 | 2022-04-26 | 8.5714 | 8.5714 | 8.5714 | 7.7143 | 0 | 6.8571 | 6.8571 | 47.1429
Hunter | 10 | 13 | 2022-04-27 | 20.5 | 30.7143 |  | 0 |  | 2022-04-27 | 7.1429 | 7.1429 | 7.1429 | 6.4286 | 0 | 5.7143 | 5.7143 | 39.2857
Luke | 9 | 11 | 2022-04-28 | 13 | 24.5714 | Other | 7.5 | 8 | 2022-04-28 | 5.7143 | 5.7143 | 5.7143 | 5.1429 | 0 | 4.5714 | 4.5714 | 31.4286
Matt | 0 | 0 | 2022-04-29 | 4 | 18.4286 | Total Predicted Work |  | 43 | 2022-04-29 | 4.2857 | 4.2857 | 4.2857 | 3.8571 | 0 | 3.4286 | 3.4286 | 23.5714
Michelle | 8 | 9 | 2022-04-30 | 1 | 12.2857 | Expected Work | Actual Work |  | 2022-04-30 | 2.8571 | 2.8571 | 2.8571 | 2.5714 | 0 | 2.2857 | 2.2857 | 15.7143
Tyler | 8 | 4 | 2022-05-01 | -1 | 6.1429 | 55 | 56 |  | 2022-05-01 | 1.4286 | 1.4286 | 1.4286 | 1.2857 | 0 | 1.1429 | 1.1429 | 7.8571
2022-04-25 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | [5 empty] | 0 | 10 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | 2 | 3 |  |  |  | 5 | 5 |  | 2022-04-25 | 10 | 5 | 8 | 7 | 0 | 5 | 4 | 39
Hunter | 2 |  |  |  |  | 2 | 8 |  | 2022-04-26 | 4 | 5 | 5 | 5 | 0 | 4 | 4 | 27
Luke | 2 |  |  |  |  | 2 | 7 |  | 2022-04-27 | 2 | 3.5 | 5 | 3 | 0 | 3 | 4 | 20.5
Matt | [5 empty] | 0 | 0 |  | 2022-04-28 | 2 | 1 | 3 | 1 | 0 | 2 | 4 | 13
Michelle | 3 |  |  |  |  | 3 | 5 |  | 2022-04-29 | 2 | -1 | -1 | -1 | 0 | 1 | 4 | 4
Tyler | 4 |  |  |  |  | 4 | 4 |  | 2022-04-30 | 2 | -1 | -3 | -1 | 0 | 0 | 4 | 1
2022-04-26 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-01 | 2 | -1 | -3 | -2 | 0 | -1 | 4 | -1
Alex | 6 |  |  |  |  | 6 | 4 |  | 2022-05-02 | 2 | -1 | -3 | -2 | 0 | -1 | 4 | -1
Daniel | [5 empty] | 0 | 5
Hunter | 3 |  |  |  |  | 3 | 5
Luke | 2 |  |  |  |  | 2 | 5
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 4
Tyler | [5 empty] | 0 | 4
2022-04-27 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | 2 |  |  |  |  | 2 | 2
Daniel |  | 1.5 |  |  |  | 1.5 | 3.5
Hunter | [5 empty] | 0 | 5
Luke | 2 |  |  |  |  | 2 | 3
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 4
2022-04-28 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel |  | 1 |  | 1.5 |  | 2.5 | 1
Hunter | 2 |  |  |  |  | 2 | 3
Luke | 2 |  |  |  |  | 2 | 1
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 2
Tyler | [5 empty] | 0 | 4
2022-04-29 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel |  | 1 |  | 1 |  | 2 | -1
Hunter | 4 |  |  |  |  | 4 | -1
Luke | 2 |  |  |  |  | 2 | -1
Matt | [5 empty] | 0 | 0
Michelle | 1 |  |  |  |  | 1 | 1
Tyler | [5 empty] | 0 | 4
2022-04-30 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel | [5 empty] | 0 | -1
Hunter | 2 |  |  |  |  | 2 | -3
Luke | [5 empty] | 0 | -1
Matt | [5 empty] | 0 | 0
Michelle | 1 |  |  |  |  | 1 | 0
Tyler | [5 empty] | 0 | 4
2022-05-01 | Individual Feature Work | Hosting/Production Environment |  | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 2
Daniel | [5 empty] | 0 | -1
Hunter | [5 empty] | 0 | -3
Luke |  |  |  | 1 |  | 1 | -2
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | -1
Tyler | [5 empty] | 0 | 4
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 0
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-04-25 | 16 | 187.1795 | 39 | 39 | 5.5714
2022-04-26 | 12 | 115.3846 | 27 | 33.4286
2022-04-27 | 6.5 | 16.6667 | 20.5 | 27.8571
2022-04-28 | 7.5 | 34.6154 | 13 | 22.2857
2022-04-29 | 9 | 61.5385 | 4 | 16.7143
2022-04-30 | 3 | -46.1538 | 1 | 11.1429
2022-05-01 | 2 | -64.1026 | -1 | 5.5714
2022-05-02 | 0 | 100 | -1 | 0

## Sprint 14
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 20 | 10 | 2022-05-02 | 73 | 58 | Individual Feature Work | 19 | 20 | 2022-05-02 | 20 | 8 | 15 | 8 | 10 | 8 | 8 | 77 |  | 1.4286 | 1 | 2.7143 | 0.71429 | 1.4286 | 0.85714 | 0.71429
Daniel | 8 | 7 | 2022-05-03 | 66 | 49.7143 | Core Requirements | 36 | 28 | 2022-05-03 | 17.1429 | 6.8571 | 12.8571 | 6.8571 | 8.5714 | 6.8571 | 6.8571 | 66
Hunter | 15 | 21 | 2022-05-04 | 57 | 41.4286 | Hosting/Production Environment | 0 | 2 | 2022-05-04 | 14.2857 | 5.7143 | 10.7143 | 5.7143 | 7.1429 | 5.7143 | 5.7143 | 55
Luke | 8 | 6 | 2022-05-05 | 48 | 33.1429 | Other | 11 | 8 | 2022-05-05 | 11.4286 | 4.5714 | 8.5714 | 4.5714 | 5.7143 | 4.5714 | 4.5714 | 44
Matt | 10 | 10 | 2022-05-06 | 37 | 24.8571 | Total Predicted Work |  | 58 | 2022-05-06 | 8.5714 | 3.4286 | 6.4286 | 3.4286 | 4.2857 | 3.4286 | 3.4286 | 33
Michelle | 8 | 7 | 2022-05-07 | 28 | 16.5714 | Expected Work | Actual Work |  | 2022-05-07 | 5.7143 | 2.2857 | 4.2857 | 2.2857 | 2.8571 | 2.2857 | 2.2857 | 22
Tyler | 8 | 5 | 2022-05-08 | 11 | 8.2857 | 77 | 66 |  | 2022-05-08 | 2.8571 | 1.1429 | 2.1429 | 1.1429 | 1.4286 | 1.1429 | 1.1429 | 11
2022-05-02 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex | [5 empty] | 0 | 20 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel | [5 empty] | 0 | 8 |  | 2022-05-02 | 20 | 8 | 13 | 7 | 10 | 7 | 8 | 73
Hunter | 2 |  |  |  |  | 2 | 13 |  | 2022-05-03 | 20 | 8 | 10 | 6 | 8 | 6 | 8 | 66
Luke |  | 1 |  |  |  | 1 | 7 |  | 2022-05-04 | 20 | 6 | 10 | 4 | 4 | 5 | 8 | 57
Matt | [5 empty] | 0 | 10 |  | 2022-05-05 | 19 | 6 | 6 | 4 | 2 | 4 | 7 | 48
Michelle |  |  |  | 1 |  | 1 | 7 |  | 2022-05-06 | 18 | 5 | 1 | 3 | 0 | 3 | 7 | 37
Tyler | [5 empty] | 0 | 8 |  | 2022-05-07 | 17 | 5 | -3 | 2 | 0 | 2 | 5 | 28
2022-05-03 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-08 | 10 | 1 | -6 | 2 | 0 | 1 | 3 | 11
Alex | [5 empty] | 0 | 20 |  | 2022-05-09 | 10 | 1 | -6 | 2 | 0 | 1 | 3 | 11
Daniel | [5 empty] | 0 | 8
Hunter | 3 |  |  |  |  | 3 | 10
Luke |  | 1 |  |  |  | 1 | 6
Matt |  | 2 |  |  |  | 2 | 8
Michelle |  |  |  | 1 |  | 1 | 6
Tyler | [5 empty] | 0 | 8
2022-05-04 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 20
Daniel |  | 1 |  | 1 |  | 2 | 6
Hunter | [5 empty] | 0 | 10
Luke |  |  |  | 2 |  | 2 | 4
Matt |  | 4 |  |  |  | 4 | 4
Michelle | 1 |  |  |  |  | 1 | 5
Tyler | [5 empty] | 0 | 8
2022-05-05 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  |  |  | 1 |  | 1 | 19
Daniel | [5 empty] | 0 | 6
Hunter | 4 |  |  |  |  | 4 | 6
Luke | [5 empty] | 0 | 4
Matt |  | 2 |  |  |  | 2 | 2
Michelle |  |  |  | 1 |  | 1 | 4
Tyler |  | 1 |  |  |  | 1 | 7
2022-05-06 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 1 |  |  | 1 | 1 | 18
Daniel |  | 1 |  |  |  | 1 | 5
Hunter | 5 |  |  |  |  | 5 | 1
Luke |  | 1 |  |  |  | 1 | 3
Matt |  | 2 |  |  |  | 2 | 0
Michelle |  |  |  | 1 |  | 1 | 3
Tyler | [5 empty] | 0 | 7
2022-05-07 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 1 |  |  | 4 | 1 | 17
Daniel | [5 empty] | 0 | 5
Hunter | 4 |  |  |  |  | 4 | -3
Luke |  | 1 |  |  |  | 1 | 2
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 2
Tyler |  | 2 |  |  |  | 2 | 5
2022-05-08 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex |  | 7 |  |  | 2 | 7 | 10
Daniel |  | 3 |  | 1 |  | 4 | 1
Hunter |  | 3 |  |  |  | 3 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle |  |  |  | 1 |  | 1 | 1
Tyler |  | 2 |  |  |  | 2 | 3
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 7
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-05-02 | 4 | -61.6438 | 73 | 73 | 10.4286
2022-05-03 | 7 | -32.8767 | 66 | 62.5714
2022-05-04 | 9 | -13.6986 | 57 | 52.1429
2022-05-05 | 9 | -13.6986 | 48 | 41.7143
2022-05-06 | 11 | 5.4795 | 37 | 31.2857
2022-05-07 | 9 | -13.6986 | 28 | 20.8571
2022-05-08 | 17 | 63.0137 | 11 | 10.4286
2022-05-09 | 0 | 100 | 11 | 0

## Sprint 15
Team Member | Expected Capacity | Actual Work |  | Actual Hours Remaining | Ideal Hours Remaining | Item | Hours Spent | Predicted | Team Ideal Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Ideal | Estimated Daily Avg. | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler
Alex | 10 | 6 | 2022-05-09 | 40 | 40 | Individual Feature Work | 0 | 10 | 2022-05-09 | 10 | 12 | 10 | 10 | 12 | 8 | 8 | 70 |  | 0 | 0.71429 | 1.4286 | 0.57143 | 0.85714 | 0.85714 | 0.42857
Daniel | 12 | 9 | 2022-05-10 | 17 | 34.2857 | Core Requirements | 49 | 10 | 2022-05-10 | 8.5714 | 10.2857 | 8.5714 | 8.5714 | 10.2857 | 6.8571 | 6.8571 | 60
Hunter | 10 | 16 | 2022-05-11 | 6 | 28.5714 | Hosting/Production Environment | 10 | 15 | 2022-05-11 | 7.1429 | 8.5714 | 7.1429 | 7.1429 | 8.5714 | 5.7143 | 5.7143 | 50
Luke | 10 | 8 |  | 6 | 22.8571 | Other | 5 | 5 | 2022-05-12 | 5.7143 | 6.8571 | 5.7143 | 5.7143 | 6.8571 | 4.5714 | 4.5714 | 40
Matt | 12 | 12 |  | 6 | 17.1429 | Total Predicted Work |  | 40 | 2022-05-13 | 4.2857 | 5.1429 | 4.2857 | 4.2857 | 5.1429 | 3.4286 | 3.4286 | 30
Michelle | 8 | 8 |  | 6 | 11.4286 | Expected Work | Actual Work |  | 2022-05-14 | 2.8571 | 3.4286 | 2.8571 | 2.8571 | 3.4286 | 2.2857 | 2.2857 | 20
Tyler | 8 | 5 |  | 6 | 5.7143 | 70 | 64 |  | 2022-05-15 | 1.4286 | 1.7143 | 1.4286 | 1.4286 | 1.7143 | 1.1429 | 1.1429 | 10
2022-05-09 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex |  | 6 |  |  |  | 6 | 4 |  | Team Actual Hours | Alex | Daniel | Hunter | Luke | Matt | Michelle | Tyler | Team Actual
Daniel |  | 1 | 2 | 1 | 1 | 4 | 8 |  | 2022-05-09 | 4 | 8 | 4 | 6 | 6 | 6 | 6 | 40
Hunter |  | 6 |  |  |  | 6 | 4 |  | 2022-05-10 | 4 | 6 | -2 | 2 | 0 | 4 | 3 | 17
Luke |  | 4 |  |  |  | 4 | 6 |  | 2022-05-11 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
Matt |  | 6 |  |  |  | 6 | 6 |  | 2022-05-12 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
Michelle |  | 2 |  |  |  | 2 | 6 |  | 2022-05-13 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
Tyler |  | 2 |  |  |  | 2 | 6 |  | 2022-05-14 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
2022-05-10 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours |  | 2022-05-15 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
Alex | [5 empty] | 0 | 4 |  | 2022-05-16 | 4 | 3 | -6 | 2 | 0 | 0 | 3 | 6
Daniel |  |  | 1 | 1 |  | 2 | 6
Hunter |  | 6 |  |  |  | 6 | -2
Luke |  | 4 |  |  |  | 4 | 2
Matt |  | 6 |  |  |  | 6 | 0
Michelle |  | 2 |  |  |  | 2 | 4
Tyler |  |  |  | 3 |  | 3 | 3
2022-05-11 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 4
Daniel |  |  | 3 |  |  | 3 | 3
Hunter |  |  | 4 |  |  | 4 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle |  | 4 |  |  |  | 4 | 0
Tyler | [5 empty] | 0 | 3
2022-05-12 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 4
Daniel | [5 empty] | 0 | 3
Hunter | [5 empty] | 0 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle | [5 empty] | 0 | 0
Tyler | [5 empty] | 0 | 3
2022-05-13 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 4
Daniel | [5 empty] | 0 | 3
Hunter | [5 empty] | 0 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle | [5 empty] | 0 | 0
Tyler | [5 empty] | 0 | 3
2022-05-14 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 4
Daniel | [5 empty] | 0 | 3
Hunter | [5 empty] | 0 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle | [5 empty] | 0 | 0
Tyler | [5 empty] | 0 | 3
2022-05-15 | Individual Feature Work | Core Requirements | Hosting/Production Environment | Other | Non-Productive Hours | Total Working Hours | Remaining Hours
Alex | [5 empty] | 0 | 4
Daniel | [5 empty] | 0 | 3
Hunter | [5 empty] | 0 | -6
Luke | [5 empty] | 0 | 2
Matt | [5 empty] | 0 | 0
Michelle | [5 empty] | 0 | 0
Tyler | [5 empty] | 0 | 3
|  |  |  | TOTAL NON PRODUCTIVE HOURS | 1
| Team Hours Worked | Percenetage Error | Hours remaining per day | Ideal avg per day | Hours Per Day To Meet Goal
2022-05-09 | 30 | 425 | 40 | 40 | 5.7143
2022-05-10 | 23 | 302.5 | 17 | 34.2857
2022-05-11 | 11 | 92.5 | 6 | 28.5714
2022-05-12 | 0 | -100 | 6 | 22.8571
2022-05-13 | 0 | -100 | 6 | 17.1429
2022-05-14 | 0 | -100 | 6 | 11.4286
2022-05-15 | 0 | -100 | 6 | 5.7143
2022-05-16 | 0 | 100 | 6 | 0