## Project Plan
| Project Title | STATUS
| What The Food? | Not Started | [5 empty] | Project Duration
| Team Leader | In Progress |  |  |  | Start Date | End Date | in Days
| Matthew Quinn | Complete |  |  |  | 2022-01-14 | 2022-05-13 | 120
On Hold
Task ID | Business Item | Status | Programmer 1 | Programmer 2 | Supporting Member | Start Date | End Date | Duration in Days | Comments
Sprint 1 Begins (01/14- 01/27)
1 | Login Page | Not Started |  |  |  | 2022-01-14 | 2022-01-27 | 14
1.1 | - Login Directory Page | Not Started | Matthew | Daniel | Tyler | 2022-01-14 | 2022-01-17 | 4 | Web page with slot for Username and Password. Create account button, and forgot password button.
1.2 | - Create Account | Not Started | Matthew | Daniel | Tyler | 2022-01-18 | 2022-01-21 | 4 | Takes in a valid email, and a password. User will get a confirmation email to activate their account.
1.3 | - Login | Not Started | Matthew | Daniel | Tyler | 2022-01-22 | 2022-01-24 | 3 | System validates email and password, if correct directs to main menu, otherwise displays incorrect login
1.4 | - Account Recovery | Not Started | Matthew | Daniel | Tyler | 2022-01-25 | 2022-01-27 | 3 | Allows a password reset email to be sent to the associated email address
2 | Main Menu | Not Started |  |  |  | 2022-01-20 | 2022-01-27 | 8
2.1 | - visually pleasing main menu page containing application name | Not Started | Michelle | Luke | Hunter | 2022-01-14 | 2022-01-20 | 7 | Main menu that will serve as the home screen to our app. The menu should be simple yet informative
2.2 | - Buttons that lead to each feature | Not Started | Michelle | Luke | Hunter | 2022-01-21 | 2022-01-25 | 5 | Buttons will be hooked up to their respective component when that module is delivered
2.3 | - News Display | Not Started | Michelle | Luke | Hunter | 2022-01-26 | 2022-01-27 | 2 | News display will be added after the news functionality is complete. A placeholder will be left in the meantime
Sprint 1 End (01/27)
Sprint 2 Start (01/28 - 02/10) 14 days
3 | Integrate Food information Database | Not Started |  |  |  | 2022-01-28 | 2022-02-10 | 14
3.1 | - Pull existing information from internet | Not Started | Matthew | Luke | Hunter | 2022-01-28 | 2022-02-02 | 6 | Withdraw product related information from the Internet.
3.2 | - Create ability to add new items easily through scanning them and taking a picture of the nutrition label | Not Started | Matthew | Luke | Hunter | 2022-02-03 | 2022-02-10 | 8 | This functionality will allow for items to be easily added into the database. This includes any new items that have been scanned that have not been registered in the database.
4 | Integrate barcode scanner API | Not Started |  |  |  | 2022-01-28 | 2022-02-10 | 14
4.1 | - Make connection to the Barcode lookup API | Not Started | Daniel | Michelle | Tyler | 2022-01-28 | 2022-02-01 | 5 | Establish a connection with Loopup which will aid with any network integration of the barcode scanner
4.2 | - Send this information from barcode to the food information database | Not Started | Daniel | Michelle | Tyler | 2022-02-02 | 2022-02-10 | 9 | Be able to update the food database by being able to send whatever information has been obtained by the barcode scanner
Sprint 2 End (02/11)
Retrospective 1
Sprint 3 Start (02/12 - 02/25) 14 days
5 | Food information page | Not Started |  |  |  | 2022-02-12 | 2022-02-25 | 14
5.1 | - Translate chemical ingredients to simple terms | Not Started | Matthew | Michelle | Tyler | 2022-02-12 | 2022-02-25 | 14 | Simplify chemical ingredients contained in a food product.Will need a dictionary of common chemical names and their translated simple version
5.2 | - Display product name, Calories, ingredients, product image | Not Started | Daniel | Luke | Hunter | 2022-02-12 | 2022-02-18 | 7 | Display all necessary information accordingly and make it so that it can adjust with any changes made the personal Calorie Tracker
5.3 | - Formatting into a pleasing manner | Not Started | Daniel | Luke | Hunter | 2022-02-19 | 2022-02-25 | 7 | Clean up the overall presentation of the Food Information to make it more user friendly
Sprint 3 End (2/25)
Milestone 1
Sprint 4 Begins (2/26 - 03/11)
6 | Scan food page | Not Started |  |  |  | 2022-02-26 | 2022-03-11 | 14
6.1 | - Access Camera to scan barcode | Not Started | Matthew | Daniel | Hunter | 2022-02-26 | 2022-02-28 | 3 | Create access from application to user camera so that user can scan their item
6.2 | - Send barcode info to database and return appropriate information | Not Started | Matthew | Daniel | Hunter | 2022-03-01 | 2022-03-05 | 5 | Be able send information of barcode so that the item information can be searched for by the database
6.3 | - load food information page with newly acquired information | Not Started | Matthew | Daniel | Hunter | 2022-03-05 | 2022-03-11 | 7 | Successfully obtain the information regarding the product and present it to the user
7 | Food flag page | Not Started |  |  |  | 2022-02-26 | 2022-03-11 | 14
7.1 | - Menu for inputting flagged items | Not Started | Michelle | Luke | Tyler | 2022-02-26 | 2022-03-02 | 5 | Include a default list of the most common items people might want to flag
7.2 | - Integrate into Food information to notify user if a flagged item is found | Not Started | Michelle | Luke | Tyler | 2022-03-03 | 2022-03-11 | 9 | Create a visible notification to create awareness for the user
Sprint 4 End (3/11)
Retrospective 2
Sprint 5 Begins (03/12 - 03/25)
8 | Food Alternatives Page | Not Started |  |  |  | 2022-03-12 | 2022-03-25 | 14
8.1 | - Page layout for displaying similar items | Not Started | Michelle | Matthew | Hunter | 2022-03-12 | 2022-03-15 | 4 | Create a simple item that will display any similar items that have been found
8.2 | - modified search criteria | Not Started | Michelle | Matthew | Hunter | 2022-03-16 | 2022-03-18 | 3 | Allow the user to select modified parameters such as lower calorie(15% lower)
8.3 | - Algorithm to identify alternatives | Not Started | Michelle | Matthew | Hunter | 2022-03-19 | 2022-03-25 | 7 | Be able to find similar products to the one being compared with. Similarities will be based on nutritional contents.
9 | Personal Cal Counter Page | Not Started |  |  |  | 2022-03-12 | 2022-03-25 | 14 | 14 days
9.1 | - page taking in needed information to calculate AMR | Not Started | Tyler | Daniel | Luke | 2022-03-12 | 2022-03-16 | 5 | Be able to accurately obtain any user input and calculate the proper results
9.2 | - store AMR to account information | Not Started | Tyler | Daniel | Luke | 2022-03-17 | 2022-03-21 | 5 | Be able to take whatever calculation has been made and store it successfully into a database
9.3 | - Integrate with food information to modify daily % values based on personal AMR | Not Started | Tyler | Daniel | Luke | 2022-03-22 | 2022-03-25 | 4 | Create compatibility with Food Information and make sure that any modifications made are adjusted accordingly
Sprint 5 Ends (03/25)
Milestone 2 (Week 11)
Sprint 6 Begins (04/02 - 04/15) Gap between sprints due to spring break
10 | History | Not Started |  |  |  | 2022-04-02 | 2022-04-15 | 14 | 14 days
10.1 | - Scrollable page containing user History | Not Started | Matthew | Daniel | Hunter | 2022-04-02 | 2022-04-05 | 4 | Create a simple, scrollable user history
10.2 | - Link to food information so a user can click on an item in their history | Not Started | Tyler | Luke | Michelle | 2022-04-06 | 2022-04-12 | 7 | Make sure compatibility between history and food information is established so that users can easily obtain information regarding any past products
10.3 | -Update user history so that it tracks the last 10 items | Not Started | Matthew | Daniel | Hunter | 2022-04-13 | 2022-04-15 | 3 | Make sure all items stored in history are correctly ordered and properly stored
Sprint 6 Ends (04/16)
Retrospective 3
Sprint 7 Begins (04/16 - 05/01)
11 | Review Page | Not Started |  |  |  | 2022-04-16 | 2022-04-29 | 14 | 8 days
11.1 | - Allow for users to leave reviews on the product they are looking at | Not Started | Hunter | Matthew | Tyler | 2022-04-16 | 2022-04-20 | 5 | Make sure user can quickly write a review about the product without restricting their opinions. Consider compatibility with profanity filter below as well.
11.2 | - Allow users to read reviews from other customers | Not Started | Hunter | Matthew | Tyler | 2022-04-21 | 2022-04-23 | 3 | Users should be able to access other user opinions with ease so that they have a general idea regarding the feedback on a product.
11.3 | - Profanity Filter | Not Started | Hunter | Matthew | Tyler | 2022-04-24 | 2022-04-25 | 2 | Make sure users cannot post anything unrelated, unsafe, unwarranted on the review page
11.4 | - Aggregate average review score from internet to set a baseline | Not Started | Hunter | Matthew | Tyler | 2022-04-26 | 2022-04-29 | 4 | Make sure to sum all review left on a product and correctly display the average score that had been made. Make sure that the average is calculated correctly as well.
12 | News Aggregation | Not Started |  |  |  | 2022-04-16 | 2022-04-29 | 14 | 8 days
12.1 | - Python web scrape new headlines together related to health | Not Started | Daniel | Michelle | Luke | 2022-04-16 | 2022-04-20 | 5 | News should be relevant to not only the product but to the consumer as well. Nothing from a personal blog or something heavily opinionated.
12.2 | - Apply headlines to the main menu | Not Started | Daniel | Michelle | Luke | 2022-04-21 | 2022-04-24 | 4 | Present news to the main menu so that user can quickly see a overview of current news
12.3 | - Algorithm to make personalized news based on user information | Not Started | Daniel | Michelle | Luke | 2022-04-25 | 2022-04-28 | 4 | Make sure news is catered specifically towards that user so that information presented is useful
12.4 | - Ability to opt out of personalized news | Not Started | Daniel | Michelle | Luke | 2022-04-29 | 2022-04-29 | 1 | Allow user to opt out if they simply do not seek this feature of the application
Sprint 7 Ends (04/29)
Milestone 3
Sprint 8 Begins (05/03 - 05/13)
13 | System wide testing | Not Started |  |  |  | 2022-04-30 | 2022-05-13 | 14
13.1 | Retest all components with intent to find obscure ways to break the application | Not Started | Tyler | Luke | Daniel | 2022-04-30 | 2022-05-06 | 7 | All portions were tested during development via automated processes. Here you will attempt to abuse edge cases to crash our application or get it to exhibit unintended behavior
13.2 | Fix any edge cases found during this last testing phase | Not Started | Tyler | Luke | Daniel | 2022-05-07 | 2022-05-12 | 6 | Any unintended behaviors found through manual exploitation will be patched here before moving into production
13.3 | Attempt to hack application and patch any exploits | Not Started | Matthew | Michelle | Hunter | 2022-04-30 | 2022-05-06 | 7 | Use inside knowledge of how the system interacts to attempt to hijack user information such as passwords or any personal information
13.4 | Fix any security vulnerabilities discovered at this time | Not Started | Matthew | Michelle | Hunter | 2022-05-07 | 2022-05-12 | 6 | If any possible methods are found, patch them and reattempt to break in. This repeats until the application is able to safely secure user information
14 | Deploy | Not Started |  |  |  | 2022-05-13 | 2022-05-13 | 1
14.1 | Release product to the public | Not Started | All team members will be present for launch party |  |  | 2022-05-13 | 2022-05-13 | 1 | Great job team!
Sprint 8 Ends (05/13)
Milestone 4

## Risk
Risk ID | Risk Type | Risk Description | Impact(1-5) | Likelyhood(%) | Risk Approach | Strategy
1 | Project Development | Due to our group members taking other courses, some objectives within out SPRINT may not be completed as scheduled | 5 | 100% | Avoidance | Our team will be utilizing Pair Programming. Due to the unpredictable nature of class schedules and work load variations having both members of a two person team free at the same times will be difficult.To maximize productive hours, 3 programmers will be assigned to tasks. While only two will ever work on the task together at any one time, having three increases the number of possible working hours.
2 | Project Execution | Project may not function as intended due to numerous people working on different portions of the project | 5 | 60% | Avoidance | We will set a firm coding standard which will be strictly followed. Furthermore, we will have frequent standup meetings to keep everyone on track with what assignment each individual is currently tasked with.
3 | Access to Resource | Existing API (barcode) stops being supported or otherwise becomes unusable | 3 | 25% | Mitigation | Find a supplementary API that has similar features to the one we were using before. Otherwise we will create our own barcode scanner which incorporates every feature we seek.
4 | Access to Resource | Chrome browser Update causes compatibility issues | 5 | 25% | Acceptance | Require users to use a supported version of chrome to use our web application
5 | Project Execution | Lack of productivity amongst group members | 4 | 5% | Mitigation | Use of scrum to uphold individual accountability and ensure steady workflow through the use of meetings and kanban boards.
6 | Project Development | Project Manager lacks organization | 3 | 10% | Mitigation | Replace Manager or scrum master with a different member
7 | Project Execution | Inaccurate Estimation of Workload | 4 | 80% | Mitigation | We will learn though each iteration how long it takes for us to complete a task and adjust accordingly by our next task.